## Sheet1
MHA MSF3 - Scope Checklist*#
* This is an ongoing list which can be added or amended throughout the contract.
# The following list is intended as a checklist of activities which may be considered when deciding on the Scope for the project. It is not intended to be exhaustive.
Item | Scheme Details | Contractor Scope Stage 1 ECI | Contractor Scope Stage 2 | Client Responsibility | Designer Responsibility | Other | Guidance | Comments
Project Details
Project Name:
Client:
Project Budget:
ECI Duration (months): | [6 empty] | Long (Early) (≥ 12 months), Medium (6 - 12 months), Short (Late) (3 - 6 months), Mobilisation Only (≤ 3 months)
Project Completion Date:
Main Designer:
Main Contractor:
Contract Type: | [6 empty] | i.e. full NEC4 including X22 or NEC4 Short Form or Professional Services etc.
Define Stage 1 and Stage 2: | [6 empty] | Only required for full NEC4 including X22
Scope
Preliminary Drawings
list land take red line drawings
list outline planning drawings
list consultation drawings
Commercial Deliverables
Project Budget | [6 empty] | (For external funding applications)
Project Cost Forecast | [6 empty] | (State frequency required) and format
Project Cost Updates | [6 empty] | (Including all Client and historical costs)
Programme Information Cl. 31.2 | [6 empty] | (state frequency of review)
Risk Register | [6 empty] | (Initial workshops and regular reviews. State frequency and who's template/system is to be used)
Take Off Quantities for Target Price | [6 empty] | (Possible external PQS)
Supply Chain Engagement & Procurement Cl. 11.2 (26)
Target Cost | [6 empty] | (State date required)
Format of Applications for Payments Cl 50.2
Performance Criteria Cl. X22.6 | [6 empty] | Activities which must be undertaken before proceed to Stage 2
Pricing Information initially submitted with MSF3 tender
Definition of Completion Cl. 11.2 (2) | [6 empty] | Review provision of as-built/H&S File information and works which can be undertaken post-Completion
Design / Design Management
Information Management
Buildability Input & Value Engineering
Options Pricing
Contractor Design Elements | [6 empty] | Consider acceptance criteria Cl.21.2 and clients rights to use design Cl.22.1
Design Management / Coordination
Design Programme Monitoring
Specialist Design (inc Temp Works) | [6 empty] | (State if external specialists to be used)
Principal Designer Duties (CDM) | [6 empty] | (Which party is to act as PD?)
Principal Contractor Duties (CDM) | [6 empty] | Any other H&S requirements Cl. 27.4
Contact with Planning Authority
Discharge Planning Conditions
Sustainability Plan - carbon reduction etc.
Buildability & VE
General Buildability Input
Value Engineering Options
Construction Programme
Planning Submission Input
Construction Phase Plans
Compounds, Storage Areas and Logistics
TM Plans and Phasing Diagrams
Cost Savings & ECI Benefits Capture - Annex G
Utilities
Obtain C3 / C4 Estimates
Utilities Coordination & Design Integration
Access and constraints relating to Utilities sharing the Working Area Cl. 25.1
Commercial Audit on Utility Costs
Stakeholder Management
Communications Plan
Statutory & Key Stakeholder Liaison
Public Exhibitions
General Public Liaison
Communications Systems - Cl 13.2
Project Visualisation
Access Issues Sharing the Working Area Cl. 25.1
Environment & Archaeology
Scoping Documents
GI Scope Identification
Development of Impact Statements etc.
Ecological surveys & Mitigation Proposals
Noise surveys
General Ecologists Environmental CoW's
Desktop Studies & Schemes of Investigation
Archaeology Field Work
Earthworks
Earthworks and Title - Cl 73
Demolition and Title Cl. 73
General Management & Systems
Document Control & Integration
Quality Management System Cl.40.1
CEMAR, CCM etc.
Employment Skills Plan
Social Value (incl Considerate Constructors)
Advanced Works
Validation of Topographical Survey
GI Field Work
Site Clearance
Utility Trial Holes
Fencing
Specification for Highway Works
Specification for Highway Works numbered appendices App 0/3
Construction drawings list Appendix 0/4
Version - MSF3 - Scope Checklist - Aug 2019 - 01
Note on A12: John Hooper: ain Contractor