## Version Control
MHA MSF3 Performance Management Toolkit
Version | Purpose | Author | Date
1 | MSF3 Tender | Mike Barnett | 2018-01-22
2 | MSF3 Project Delivery | Mike Barnett | 2019-09-18
3 | MSF3 Project Delivery | Mike Barnett | 2020-01-06

## Introduction
MHA MSF3 Performance Management Toolkit
Introduction |  | How to use the toolkit
1.1 | The performance of the project team delivering the project should be rated and monitored by the whole project team in relation to each Works Order carried out under the Framework Agreement. This assessment will be carried out against each of the quality criteria and the accuracy of any Cost Models used in the selection procedure. These performance and accuracy scores will then be used to adjust the current quality scores for the Contractor for all live projects that are more than six months past the first access date - this relates to Stage 2 KPIs only. | 2.1 | The toolkit is designed to enable scores to be entered into each of the worksheets for the key criteria plus, Scheme Details. Enter the required information into the relevant coloured cells within the Scheme Details worksheet and, worksheets 0 to 11.
1.2 | The ten key quality aspects are Product, Service, Right First Time, Cost Management, Time, Safety, Social Value, Community, Traffic Management, Innovation and Quality for Money. |  | Information about the Scheme to be entered the first time the toolkit is used or when a specific task has been completed (that is only done once and used to capture the data). This information should be entered into cells in the Scheme Details worksheet coloured grey.
1.3 | In addition to the key quality aspects, there are performance elements that measure the performance of the Commissioning Authority and, the toolkit also includes the MHA Framework Community KPI's. |  | In the Scheme Details worksheet, orange cells denote data that will normally be updated each time performance measures are scored including at monthly intervals during the project and, following completion of the project.
1.4 | This spreadsheet contains definitions and guidance on the key performance measures and a toolkit that can be used to collect the required information for each work package both during and at the end of the scheme. |  | Worksheets 0 to 11, green cells denote data that will normally be updated each time performance measures are scored at monthly intervals during the project and, following completion of the project, unless specified otherwise.
1.5 | For each key quality aspect a number of measures have been defined. |  | A cell coloured blue with a dashed border in the Scheme Details worksheet is calculated data. Blue cells in a KPI worksheet are linked to the relevant data from the Scheme Details eg 4_Cost Management.
| Core measures are expected to be collected for all schemes both during and at the end of the scheme. In scheme core measures are collected at monthly intervals from the start of work on site, unless specified. |  | Optional measures are entered into cells coloured aqua.
| Optional - locally determined are measures that teams may wish to adopt locally for Works Orders. The use of these measures needs to be agreed before the start of a scheme. These measures are not used to adjust the quality scores of an individual Contractor. |  | The majority of the worksheets are protected against amending or altering content and in the case of satisfaction scores the range of scoring that can be used. Data can generally only be entered into the coloured cells described above.
| Framework - are measures which are collected and reported at a framework level. These measures are not used to adjust the quality scores of an individual contractor. | 2.2 | Where appropriate the spreadsheet will automatically convert the scores entered into an MHA score out of 10. For example, the Considerate Constructors score in 8_Community will normally be the overall scheme score issued following the Monitors visit. This will then be converted to an MHA score and the MHA Multiplier used to adjust the quality scores used for Contractor Selection. The relationship between the score and the multiplier is generally shown on each worksheet. Where the conversion data is not shown on the individual worksheet the relevant worksheet containing the data is referenced to ensure that the methodology is transparent to all users.
1.6 | The toolkit contains a number of worksheets as described below | 2.3 | The summary information from each of the worksheets 1 to 11 is automatically transferred to the Scheme Scores worksheet and the Optional Scores worksheet.
| Introduction | 2.4 | Each time a new set of scores is entered the data in the spreadsheet will be updated. To keep a history of past scores it is a requirement that the spreadsheet is saved as a new version each time updated scores are entered. To keep a history of the project the previous data in the Scheme Scores worksheet and Optional Scores worksheet should be copied across to a new column (see 2.5 below). It is recommended that each version of the file is saved using the following filename convention. YYYYMMDD_MHA Ref_Scheme Title_Contractor Name_Version No. For example 20171021_001_Gedling Access Road_Balfour Beatty_V2
| Scheme Details - Core scheme details including key cost, time and safety data, and current data about scheme including date of scoring. | 2.5 | Before updating the scores, in the worksheet Scheme Scores, select column H and then insert a new empty column. Next select and copy column G (latest scores). Finally using Paste Special - Values, paste the copied data into the inserted blank column. Add the date (MMM-YY) of the previous update into this column in cell H8 . Once this is complete continue to enter the latest set of information into the spreadsheet. Repeat the above process for the Optional Scheme Scores worksheet if Optional Measures are being collected. There will then be a record of previous scores in the toolkit.
| Scheme Scores - A summary of the latest set of scores contained in each of the worksheets and a summary of past scores collected at monthly intervals. | Guidance on scores
| Scheme Scores - Charts - Charts for each KPI based on the data in the Scheme Scores worksheet. | 3.1 | Wherever possible, scores are derived direct from objective data eg Considerate Constructors score, predictability of cost and time
| Optional Scheme Scores - A summary of the latest set of optional scores contained in each of the worksheets and a summary of past scores collected at 2 month intervals. | 3.2 | Where objective scoring is not available, guidance on how to score is provided within each of the relevant worksheets 1 to 11. This can normally be found in the lower half of the worksheet.
| Optional Scheme Scores - Charts - Charts for each optional measure based on the data in the Optional Scheme Scores worksheet. | 3.3 | Coloured cells where scores are entered generally have data validation built in. For example, scores against key aspects based on satisfaction will generally only allow scores against the numbers indicated. This is to encourage positive and collective decisions around scores to aid distinction between different levels of performance.
| MHA MSF3 KPI's - A summary of the KPI's and Optional Measures including definitions, indicator type, frequency of collection. The worksheet is set up with a filter on the top row. | 3.4 | A score of 8 generally indicates that a scheme is performing at the level expected by the MHA. Where a scheme scores higher or lower than 8 it is expected that comments will be provided to outline the reasons for either higher or, lower levels of performance. A comments box is provided for this purpose on each worksheet
| 1_Product - Satisfaction with key aspects of product | 3.5 | Please Note: The default starting score should be 8 every month, if in a previous assessment a higher score was awarded then the project team need to consider whether the reasoning for the higher score is still valid or update the narrative to support the score.
| 2_Service - Satisfaction with key aspects of service | In scheme scores
| 3_Right First Time - Looks at the 'whole system' to ensure right first time. Is there a plan, is it communicated, how effectively is it deployed, what level of failure or non-conformity is arising. | 5.1 | In scheme scores are to be collected monthly from the start of work on site and submitted to the MHA Framework Manager. The core measure scores are converted to the MHA MSF3 quality multiplier.
| 4_Cost Management - Predictability of cost | 5.2 | The MHA MSF3 quality multiplier during the scheme will be calculated as the average of the scores to date and this will be used to adjust the tender quality score used for primary selection. The score will be adjusted at the end of the scheme based on the average score during the Works Order, in the event of schemes having distinct and different phases the score will be adjusted at the end of each phase.
| 5_Time - Predictability of time | Guidance on key aspects or factors
| 6_Safety - Key aspects of health and safety | 6.1 | Where scoring depends on the consideration of 'key aspects or factors' these are listed in the lower half or the spreadsheet below the guidance referred to in 3.2 above.
| 7_Social Value - Engagement with Employment and Skills Plan and measure of the social, economic and environmental benefits for the local area operated in. | Other worksheets in the toolkit
| 8_Community - Impact of projects on the local community | 7.1 | In addition to the worksheets described above, the spreadsheet also contains a number of other worksheets that are used to provide background data to support the calculation of the MHA score eg Considerate Constructors. Where any changes to the scoring mechanism are agreed by the MHA Framework Community Board these will be updated and a new version of the toolkit issued.
| 9_Traffic Management - Key aspects of traffic management | Printing
| 10_Innovation and Value for Money | 8.1 | Pages are generally formatted to print out on A4 or A3 paper. For worksheets 1 to 11 the pages are generally formatted to print the MHA Score, Scheme Score, Guidance on satisfaction score and, key aspects/factors on individual pages allowing the user to print out as much or, as little as required.
| 11_Commissioning Authority Performance - Review of Commissioning Authority performance | Further information
|  | 9.1 | For further information on the MHA Quality Aspects and training or guidance on the toolkit please contact John Hooper, MHA Framework Manager, Tel : 0116 305 7873 email: john.hooper@leics.gov.uk
1.7 | The spreadsheet allows the direct recording of all Core and Optional measures. Whilst suggestions for Optional -Locally Determined measures are included within each of the worksheets 1 to 10 and are carried forward to the Optional Scheme Score Summary they are not used to amend the MHA MSF3 Quality score multiplier. Optional measures should only be used with the agreement of the whole project team but can be a further way of measuring success against the MHA outcomes. | 9.2 | For further information on the use of the toolkit or any issues that arise with the use of the toolkit please contact Mike Barnett, Team Manager Major Project and Improvements, Via East Midlands Limited, Tel : 0115 977 3118 email : mike.barnett@viaem.co.uk
1.8 | The ten worksheets containing the MHA quality criteria are generally formatted in the same way and include a summary MHA score and multiplier, cells to enter core and optional measures, satisfaction criteria (where appropriate) and, key aspects/factors. A typical layout is shown below for 3_Right First Time

## Scheme Details
Scheme Details
Information on first use of Toolkit |  | Unit/Format | KPI | Notes on information required | Relevant NEC guidance notes
Client |  |  |  | Name of Client (MHA Commissioning Authority), defined in Contract Data Part 1 | This is the Client's legal name.
Client's Representative |  |  |  | Name of Client's Representative
Project Manager |  |  |  | Name of Project Manager, defined in Contract Data Part 1
Supervisor |  |  |  | Name of Supervisor, defined in Contract Data Part 1
Midland Highways Alliance (MHA) Ref |  |  |  | Reference number for Works Package, 3 digit number provided by MHA at approval of Annex B
Scheme Title |  |  |  | Name of Works Package
Contractor |  |  |  | Name of Contractor, defined in Contract Data Part 2
Contractors Key Person 1 |  |  |  | Name of Key Person 1, defined in Contract Data Part 2
Contractors Key Person 2 |  |  |  | Name of Key Person 2, defined in Contract Data Part 2
Contractors Key Person 1 (X22) |  |  |  | Name of Key Person 1, defined in Contract Data Part 2 for X22 Early Contractor
Contractors Key Person 2 (X22) |  |  |  | Name of Key Person 2, defined in Contract Data Part 2 for X22 Early Contractor
Contractors Key Person 3 (X22) |  |  |  | Name of Key Person 2, defined in Contract Data Part 2 for X22 Early Contractor
Annex A award date |  | DD-MM-YYYY | X22.5 | This is the date when the Framework Manager confirms the outcome and preferred Contractor following submission of the Annex A form to the MHA
Expected Start Date for Stage 1 |  | DD-MM-YYYY | X22.5 | This is the date set on the Annex A form
Planned Duration for Stage 0 (to enter Stage 1) | 0 | Weeks | X22.5 | This is the planned number of weeks to enter Stage 1 from the date that the Contractor is confirmed following the submission of the Annex A to the MHA to the expected start date for ECI included in the Annex A
Annex B award date |  | DD-MM-YYYY |  | This is the date when the Framework Manager confirms the outcome of the submitted Annex B form to the MHA (this required MHA Board approval)
Starting Date |  | DD-MM-YYYY | X22.5 and X22.7 | This is the starting date, defined in Contract Data Part 1 and is the date that the contract actually starts, for most MSF3 projects this will also be the start date for Stage 1 due to the use of X22. | The starting date is the earliest date from which the Contract starts Providing the Works. This may be a date before or on the same day as the earliest access date.
Actual Duration for Stage 0 (to enter Stage 1) | 0 | Weeks | X22.5 | This is the actual number of weeks to enter Stage 1 from the date that the Contractor is confirmed following the submission of the Annex A to the MHA to the expected start date for ECI included in the Annex A
Access Date |  | DD-MM-YYYY | X22.7 | This is the access date, defined in Contract Data Part 1 and is the date that the construction works can start, for most MSF3 projects this will be the planned start date for Stage 2 due to the use of X22 and will be fixed once the notice to proceed is issued. If access to the whole Site is not available, this should be the first access date. | The access date is the earliest date from which the Contractor can start work on the Site. The Contractor can identify a later date from which he plans to access the Site on the Programme. It may not be possible for the Client to give the Contractor access to the whilst Site on the same date. If necessary, more that one date can be identified for difference parts of the Site from when the Contractor can access each part.
Budget (on entering Contract) |  | £ | X22.9 | The budget represents the cost of the project which the Contractor can control or influence, this may be defined in Contract Data Part 1 or the Scope. This may be different to the budget that the Client has that may include other costs such as land, preparatory fees, design fees etc.
The Works Cost |  | £ | X22.10 | The Works cost is Contract costs, the methodology for how this is derived is set by the project team as part of agreeing the Contract, but is effectively a combination of the Forecast Stage 1 Costs plus Forecast Stage 2 Costs.
Does the Works Oder include the secondary option X22 |  |  |  | The options are Yes or No, the decision to use X22 as a secondary option clause is made by the commissioning authority, the framework requires that the MHA is notified of its inclusion on the Annex B form when submitted for approval.
Information at monthly intervals & end of scheme | Period covered by this submission
Period covered by data in toolkit (from) |  | DD-MMM-YY |  | Period covered by performance data in the toolkit, normally the latest monthly period during scheme or, insert when the "final scores" are completed at end of scheme.
Period covered by data in toolkit (to) |  | DD-MMM-YY
Stage 1 (X22)
Planned Duration (Stage 1) | Cells C20 and C22 require completion | Weeks | X22.7 | This is the length of time in weeks between the starting date and the access date defined in Contract Data Part 1
Actual Start Date (Stage 1) |  | DD-MM-YYYY | X22.7 | This will typically be the starting date stated in cell C20 from Contract Data Part 1, this is contractual and can only be by the Client and Contractor by mutual agreement and likely as a Deed of Variation.
Actual End Date (Stage 1) |  | DD-MM-YYYY | X22.7 | This will typically be the date that the construction works start and will either be the access date defined in Contact Data Part 1 (if going to programme) or an alternative access date as agreed in Stage 1 and included in the notice to proceed. Or, it can be earlier than the access date if construction is delayed (such as for land or funding), but Stage 1 is defined as completed for the purpose of the Contract.
Actual Duration (Stage 1) | Cells C33 and C34 require completion | Weeks | X22.7 | This is the length of time between the actual start and end dates of Stage 1
Forecast Costs (Stage 1) |  | £ | X22.8 | Agreed forecast Stage 1 costs. Please note: There is nowhere in Contract Data Part 2 to insert the forecast - It is suggested that this is appended as supplementary data to the Annex B information submitted to the MHA for approval.
Actual Costs (Stage 1) |  | £ | X22.8 | Certified Stage 1 final costs.
The total of the Prices for Stage 2 |  | £ | X22.6 | Agreed total of the Prices for Stage 2 costs - this in the Initial Target Price that will have been included in the notice to proceed. | The total of the Prices for Stage Town is assessed by the Contractor using the Pricing Information stated in the Contract Data.
Planned Start Date of Stage 2 |  | DD-MM-YYYY |  | Planned start date for construction, either on or after the access date as defined on Contract Data Part 1 or alternative start date agreed during ECI.
Planned - Construction period of Stage 2 |  | Weeks |  | Programme length in weeks defined in Contract Data Part 2 or agreed during Stage 1, this needs to be agreed prior issuing the notice to proceed - this will be from the programme.
Notice to proceed to Stage 2 |  | DD-MM-YYYY |  | This is the date that the Project Manager issues to the notice to proceed to the Contractor. | X22.5 (1) The Project Manager issues a notice to proceed to Stage Town when the Contractor has obtained approvals and consents from Others as stated in the Scope, changes to the Budget have been agreed or assessed by the Project Manager, the Project Manager and the Contractor have agreed the total of the Prices for Stage Two and the Client has confirmed the works are to proceed.
Annex G - Agreed ECI Savings during Stage 1 |  | £ | X22.6 | This is the value of the savings agreed on the Annex G form that requires to be submitted to the MHA following ECI and completion of Stage 1, these savings need to be agreed by the project team and signed off by the Project Manager.
Percentage of agreed ECI savings against Initial Target Cost | Cells C38 and C42 require completion | % | X22.6 | Value of savings identified during ECI and expressed as a percentage of the Initial Target Price agreed at the time of issuing the Notice to Proceed to Stage 2, Annex G should be submitted to MHA upon completion.
Budget (at entering Stage 2) |  | £ | X22.9 | The budget represents the cost of the project which the Contractor can control or influence, this may be defined in Contract Data Part 1 or the Scope. This may be different to the budget that the Client has that may include other costs such as land, preparatory fees, design fees etc. This is the budget that is used at issuing the Notice to Proceed to Stage 2 as it may have changed following the period of ECI and completion of Stage 1.
Stage 2 (Construction)
Time
Programme Start Date (Stage 2) - Actual |  | DD-MM-YYYY |  | This is the start date as agreed and identified on the accepted programme that is in place for the start of Stage 2.
Programme End Date (Stage 2) - in place at Start of Stage 2 |  | DD-MM-YYYY |  | This is the end date as agreed and identified on the accepted programme that is in place for the start of Stage 2 - this will be Completion (of the project).
Programme Duration (Stage 2)- in place at Start of Stage 2 | Cells C48 and C49 require completion | Weeks |  | This is the length of time in weeks between the programme start and end dates from the accepted programme that is in place for the start of Stage 2.
Latest Agreed Programme End Date (Stage 2) |  | DD-MM-YYYY |  | This is Completion as identified on the latest accepted programme taking into account any change in the end date as a result of accepted and assessed compensation events.
Latest Agreed Programme Duration (Stage 2) | Cells C48 and C51 require completion | Weeks |  | This is the length of time in weeks between the programme start date for Stage 2 to latest agreed programme end date.
Latest (and at end of scheme final) estimated Programme End Date (Stage 2) |  | DD-MM-YYYY |  | Latest Planned Completion (and at end of scheme final) as shown on the accepted programme.
Latest Duration (Stage 2) | Cells C48and C53 require completion | Weeks |  | This is the length of time in weeks between the programme start date for Stage 2 latest estimated programme end date.
Variation of time - percentage variance of latest to agreed duration | Awating Completion of Date Information | % | 5.2 | This usees the latest programme duration based on the estimated programme end date (cell C53) - agreed duration (cell 51) / agreed duration (cell 51).
Total Agreed Extension |  | Days |  | Number of days extension to accepted programme (includes weekends and bank holidays) - this will be known once compensation events have been accepted and assessed.
Agreed Extension due to change in scope eg an additional phase to the project notified by the Project Manager |  | Days |  | Agreed extension due to change in scope eg an additional phase to the project notified by the Project Manager.
Service
Number of Payments to Supply Chain made within 7 days or less of the Assessment date within period |  | No. | 2.3 | Used to calculate Service measure 2.3 - percentage of payments to supply chain within 7 days, expressed as percentage of total supply chain payments in assessment. period (values collected should be within the period covered by the Toolkit)
Total Number of Payments made to Supply Chain within period |  | No.
Financial
Initial Target Price | 0 | £ | X22.6, X22.10 and 10.1 | This the total of the Prices for Stage 2, agreed in Stage 1 if X22 clause is used, data from cell 38.
Total Initial Value of agreed Compensation events within period |  | £ |  | The figure used should be the total of the initial value for Compensation events agreed within the period covered by the Toolkit, if a compensation event was notified before the current period but agreed within the period then it should be included.
Total Agreed Value of agreed Compensation events within period |  | £ |  | The figure used should be the total of the agreed value for Compensation events agreed within the period covered by the Toolkit, if a compensation event was notified before the current period but agreed within the period then it should be included.
Total Initial Value of agreed Compensation events to date |  | £ | 4.2 | The total initial value (based on quotation) of all compensation events notified by the Project Manager and the Contractor.
Total Agreed Value of agreed Compensation events to date |  | £ |  | The total final agreed value (based on assessment) of all compensation events notified by the Project Manager and the Contractor.
Accurately priced compensation events | Cells C67 and C68 require completion | % |  | (Total Agreed Value of Compensation Events agreed within the period - Total Initial Value of Compensation Events within the period) / Total Agreed Value of Compensation Events agreed within the period.
Total Number of Compensation events notified to date |  | No. | 4.3 | The total number of all compensation events notified by the Project Manager and the Contractor.
Total Number of notified Compensation events agreed to date |  | No. |  | The total number of all agreed compensation events notified by the Project Manager and the Contractor
Agreed compensation events | Cells C70 and C71 require completion | % |  | Total number of notified compensation events (cell C69) / Total number of agreed compensation events (cell 70)
Total Agreed Value of agreed Compensation events due to change in scope eg additional phase to project |  | £ |  | The final agreed value of all compensation events notified by the Project Manager that are due to a significant change in scope in the works eg the award of an additional phase to the project through a change in Scope.
Latest forecast target price (and at the end of the scheme the final adjusted target price) |  | £ | 4.1 | Latest in scheme adjusted target price (this should be Initial Target Price plus total agreed value of compensation events).
Latest predicted outturn cost (and at the end of the scheme outturn cost) |  | £ | 4.1 & 3.3 | Latest in scheme predicted outturn cost.
Predictability of cost | Cells C74 and C75 require completion | % | 4.1 | (Latest predicted outturn cost - Latest predicted target cost) / Latest predicted target cost.
Latest Value of cumulative savings identified from Innovation Register |  | £ | 10.1 | The total value of savings identified and agreed between the Project Manager and Contractor on the Innovations Register.
Safety
Total No. of hours worked on site since construction started |  | No. |  | Used to calculate overall framework measures
Total No. of hours worked on site in period (since last report). |  | No. |  | Used to calculate overall framework measures
Number of RIDDORS in period (since last report) |  | No. |  | Used to calculate overall framework measures
Number of Lost Time Accidents in period (since last report) |  | No. |  | Used to calculate overall framework measures
Total number of exceptions recorded using a Non Conformance Process |  | No. |  | See MHA Quality Charter
Number of exceptions recorded in period ie past month |  | No. |  | See MHA Quality Charter
Total Number of NCR's closed out in the agreed timescale |  | No. |  | See MHA Quality Charter
No of NCR's per £100k | Cells C75 and C84 require completion | No/£100k | 3.3 | Total number of exceptions recorded using a Non Conformance Process (cell C83)/(Latest predicted outturn cost (and at the end of the scheme outturn cost) (cell 74)/100000)
Percentage of NCR's closed out in the agreed timescale | Cells C84 and C86 require completion | % | 3.4 | Total number of exceptions closed out in the agreed timescale (cell C85) / Total number of exceptions recoded using a Non Conformance Process (cell C83)
Calculated Data
Toolkit Completed By
Completed By (Project Manager)
Completed By (Client)
Completed By (Contractor)
Date of Completion
Comments
Note on G23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The NEC4 Volume 2 Guidance Notes suggests the Budget is set out in the Scope. Managing the Budget in this way gives the Project Manager control over the Budget and helps better manage the use of contingencies. Furthermore we are unable to predict what “additional events” [X22.6] may change the budget. If the budget were included in the Contract Data and an unpredicted event not arising from the Project Manager giving an instruction changing the Client’s requirements stated in the Scope, were to cause the actual scheme budget to change, the Project Manager would be unable to make the necessary amendment to the Budget. By including the Budget in the Scope, the Project Manager is able to change the Scope and therefore the Budget, facilitating us to properly react to these unpredicted events.
Note on G44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The NEC4 Volume 2 Guidance Notes suggests the Budget is set out in the Scope. Managing the Budget in this way gives the Project Manager control over the Budget and helps better manage the use of contingencies. Furthermore we are unable to predict what “additional events” [X22.6] may change the budget. If the budget were included in the Contract Data and an unpredicted event not arising from the Project Manager giving an instruction changing the Client’s requirements stated in the Scope, were to cause the actual scheme budget to change, the Project Manager would be unable to make the necessary amendment to the Budget. By including the Budget in the Scope, the Project Manager is able to change the Scope and therefore the Budget, facilitating us to properly react to these unpredicted events.

## 0_X22 - Stage 1 KPIs
Scheme Title | 0 | MHA Ref | 0 |  |  | Note:
Contractor | 0 | Commissioning Authority | 0 |  |  | Performance Measures are to be measured, but are not used by the MHA to adjust Contractor Quality Submissions, therefore no multiplies are used.
Period | 0 | To | 0
| Measure | Score | Method | Frequency | Comments
X22.1 | Satisfaction against key aspects of service |  | Satisfaction against key aspects | In Project - Monthly intervals & within 4 weeks of the end of Stage 1
X22.2 | Satisfaction against key aspects of product |  | Satisfaction against key aspects | In Project - Monthly intervals & within 4 weeks of the end of Stage 1
X22.3 | Satisfaction against key aspects of value for money |  | Satisfaction against key aspects | In Project - Monthly intervals & within 4 weeks of the end of Stage 1
X22.4 | Satisfaction against key aspects of provision of cost information |  | Satisfaction against key aspects | In Project - Monthly intervals & within 4 weeks of the end of Stage 1
To help understand performance, please provide comments for the above KPIs for a score other than eight
X22.5 | Predictability to Time for Stage 0 - % change of time to enter Stage 1 | Complete Scheme Details at end of Stage 1 | Percentage change considering the actual time taken to agree the Scope and enter into Contract against the planned time to enter into Contract (as set out on Annex A). NB: -ve number indicates completed earlier than planned | At the start of Stage 1 at the first In Project meeting
X22.6 | Innovation Savings as a percentage of initial target price | Please complete Scheme Details | ECI Savings Register in place and supplied to MHA as part of Annex G, expressed as the value of ECI as a percentage of initial target price (total of the Prices for Stage 2) | At end of Stage 1, following issuing of Notice to Proceed
X22.7 | Predictability to Time for Stage 1 - % change of time to complete Stage 1 | Please complete Scheme Details | Percentage change of the actual time taken to complete Stage 1 against the planned time to complete as stated in Contract Data Part 1 | At end of Stage 1, following issuing of Notice to Proceed
X22.8 | Predictability to Cost for Stage 1 - % change of forecast to actual cost | Please complete Scheme Details | The actual cost to complete Stage 1 measured against the estimated cost stated in the Contract Data Part 1 | At end of Stage 1, following issuing of Notice to Proceed and agreement of costs
X22.9 | Predictability to Cost - % change of Budget | Please complete Scheme Details | The Budget at Stage 1 measured against the Budget confirmed for Stage 2 | At end of Stage 1, following issuing of Notice to Proceed
X22.10 | Predictability to Cost - % change of Works Costs | Please complete Scheme Details | The agreed Initial Target Price agreed at end of Stage 1 measured against the estimated Works cost stated in the Budget | At end of Stage 1, following issuing of Notice to Proceed
Score | Question | Guidance on scoring
0 | Totally dissatisfied | No commitment has been made by the Contractor to the Stage 1 KPI being assessed. The Project Manager will have written to the suppliers Director and the MHA Manager and the matter will have been discussed at the Framework Community Board.
2 | Very dissatisfied | The Contractor has made little progress on the delivery of the Stage 1 KPI being assessed. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board.
4 | Dissatisfied | Most aspects of Stage 1 KPI being assessed are unacceptable and outweigh those which are satisfactory to the extent that the Project Manager sought improvement, but limited action was taken by the Contractor.
5 | Slightly dissatisfied | Some minor aspects of the Stage 1 KPI being assessed are unacceptable and outweigh those which are satisfactory to the extent that the Project Manager sought improvement, but following investigation the nature of the KPI shown opportunities to progress to be limited.
6 | Neither satisfied or dissatisfied | The Stage 1 KPI being assessed is in progress but, the Project Manager is neither satisfied or dissatisfied with of the Contractor to take this forward.
7 | Fairly satisfied | The Contractor demonstrates a commitment to the developing Stage 1 KPI being assessed and has implemented some of the aspects identified.
8 | Satisfied | The Contractor demonstrates an adequate commitment to developing the Stage 1 KPI being assessed in line with the commitments made at Framework Tender Stage and, individual work package requirements.
9 | Very satisfied | The Contractor demonstrates an good commitment to developing the Stage 1 KPI being assessed and successfully implements most of the aspects identified and shares the success with the Framework Community
10 | Exceptionally satisfied | The Contractor demonstrates an excellent commitment to developing the Stage 1 KPI being assessed and successfully implements all the aspects identified and captures and shares the success with the Framework Community.
Key Aspects
| Service | Product | Value for Money | Cost Information
| Review per-construction information and liaise with Designer to 'design out'. Identify all 3rd parties and includes discussion on quality. Quality Plan put in place pro-actively and continually review. Ensure all staff involved in Stage 1 understand project specific requirements regarding quality. Regular reviews and checks against framework and project KPIs. Review and discuss selection processes to enable selection of quality subcontractors and suppliers. Involvement of local small and medium enterprises (SME) in Stage 1. | Compliance with Stage 1 scope. Outstanding information produced in Stage 1 to feed into Stage 2. Early warning register, kept up to date, reviewed regularly and ongoing dialogue at review meetings. Compliance with quality statements relevant to work package made in original framework submission. Explore opportunities throughout ECI, revised regularly and ongoing dialogue at workshops and project meetings. | Early Contractor and Supplier involvement. Identify savings and opportunities throughout the process. Pull value and innovation up through supply chain. Culture and demonstrable commitment to project and its success. | Provision of accurate and timely information for Stage 1 cost and prices for Stage 2. Compliance with Scope. Proactive with identifying cost savings and regularly review position.

## MHA MSF3 Stage 2 KPI's
| Category | Purpose | Factors/Key Aspects |  | Measure | Type | Method | Applies to | Frequency | Comments | Source of data
1 | Product | To determine the overall level of Client satisfaction with the completed product. | Construction of main works; handover, acceptance, inspections and as-built records; post-project review; risk & opportunities register; sustainable construction, minimising waste creation and maximising recycling and opportunities plan. | 1.1 | Percentage satisfaction against key aspects of product | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | In scheme progress and end of scheme review meeting
2 | Service | To determine the overall level of Client satisfaction with the service of the supplier during the project. | Organisation and management; procurement of specialists and suppliers; supply chain; management and improvement of Client relationships; management and improvement of customer and third party relationships; innovation and value for money; management of change; collaborative working. | 2.1 | Satisfaction against key aspects of service | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | In scheme progress and end of scheme review meeting
2 | Service | To ensure that the Supply Chain receive prompt payment |  | 2.2 | Supply chain payments - percentage of payments to supply chain made within 7 days of the assessment date | Core | Percentage of payments to supply chain made within 7 days of the assessment date | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | To ensure prompt payments to Tier 2 and 3 supply chain | Expressed as a percentage of total supply chain payments
2 | Service |  |  | 2.3 | Percentage satisfaction of Tier 2 suppliers with MHA Framework Contractor against MHA standard questionnaire | Optional - Locally determined | Post scheme satisfaction survey carried out by MHA Framework Contractor maximum 4 weeks after completion of scheme. Survey to be developed from framework contractor's existing processes. | Scheme | End of scheme
3 | Right first time | To assess the impact on the Client of any defects and reworking. | Avoiding defective works; quality management system. | 3.1 | Satisfaction with key aspects that reduce the risk of defects in construction | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | In scheme progress and end of scheme review meeting
3 | Right first time |  |  | 3.2 | Percentage of disallowed costs due to works not complying with the Scope against adjusted target | Optional - Locally determined |  | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | Payment assessment
3 | Right first time |  |  | 3.3 | No of NCR's per £100k | Optional - Locally determined |  | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | From QMS and scheme details
3 | Right first time |  |  | 3.4 | Percentage of NCR's closed out in the agreed timescale | Optional - Locally determined | Calculated by Contractor | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | From QMS
4 | Cost management | To measure the accuracy of cost predication and reliability of cost control. | Ensuring accurate estimating and forecasting, predictability of cost, and accuracy of cost and payment records. | 4.1 | Predictability of cost | Core | Percentage variation of cost against adjusted target price | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | The calculated percentage is also used to determine the pain / gain share as defined in Framework Contract Data Part 1 | Contract data as adjusted
4 | Cost management | To measure the accuracy of cost predication of change. |  | 4.2 | Accurately priced compensation events | Core | Percentage variation of cumulative initial value of submitted CE's to the final agreed value of those same events | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | Based on Compensation Event initial values submitted by the Contractor and the final value reviewed and agreed with the Commissioning Authority | From EWN/CE register
4 | Cost management |  |  | 4.3 | Percentage of number of compensation events agreed in relation to the number submitted | Optional - Locally determined | From EWN/CE register | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | From EWN/CE register
4 | Cost management | Cost Performance |  | 4.4 | Comparison of budget cost of work to actual cost of work performed (percentage) | Optional - Locally determined | Comparison of budgeted cost of work to actual cost of work performed | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | From payment application and accepted programme
4 | Cost management |  |  | 4.5 | Accuracy of cost and payment records expressed as a percentage | Optional - Locally determined | From audits of submitted cost information | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
5 | Time | To measure the reliability of time estimates for both design and construction. | Reliability of programming; predictability of time. | 5.1 | Percentage satisfaction against key aspects of product | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | In scheme progress and end of scheme review meeting
5 | Time |  |  | 5.2 | Predictability of time | Optional - Locally determined | Percentage variation of forecast duration against agreed programme | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | Accepted Programme
5 | Time |  |  | 5.3 | Reliability and accuracy of programming of activities | Optional - Locally determined | Programmed activities complete as a percentage of activities due to be complete | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | Calculated by Contractor and agreed with Project Manager | Accepted Programme
5 | Time |  |  | 5.4 | Accuracy of duration for compensation events | Optional - Locally determined | Ratio of agreed cumulative requests (as a percentage) for additional time compared to the submitted periods of those CE's | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | Calculated by Contractor and agreed with Project Manager | From CE register
6 | Safety | To measure health and safety aspects on the project. | Health, welfare and development of the workforce; compliance with safety legislation and regulations; safety of the public. | 6.1 | Percentage satisfaction against key aspects of safety | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | In scheme progress and end of scheme review meeting
7 | Social Value | To monitor the engagement with the ESP to help ensure successful of skills development against the Employment and Skills Plan (ESP). | New entrant’s skills development, existing workforce skills development, progression into employment | 7.1 | Contractors engagement in the Employment and Skills Plan | Core | Satisfaction against level of engagement, approach and likelihood of achieving targets. | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | In scheme progress and end of scheme review meeting
7 | Social Value | To measure the success of skills development against the Employment and Skills Plan (ESP). |  | 7.2 | Percentage of ESP activities where agreed targets set have been achieved | Core | Achievement of agreed targets set in the ESP measured on an activity level | Scheme | End of scheme |  | Contractors ESP plan and record of targets achieved against agreed targets, measured on an activity level
7 | Social Value | To provide an overall measure of the social, economic and environmental benefits for the local area the scheme is delivered within. |  | 7.3 | Building Social Value Assessment | Report is a Framework Requirement | Building Social Value Inspection Report at end of scheme | Scheme | End of scheme |  | BSV Assessment
8 | Community | To measure how the impact of projects on the local community is minimised before, during and after completion. | Customer Care, working with the local community, Considerate Constructor. | 8.1 | Considerate Constructors Score (CCS) | Core | Considerate Constructors Scheme Inspection | Scheme | Latest score from CCS Monitor visit | The scheme score is based on the most recent CCS report | CCS Score
8 | Community |  |  | 8.2 | Overall satisfaction with construction of the works (percentage) | Optional - Locally determined | Frontage scheme and stakeholder satisfaction survey | Scheme | End of scheme
8 | Community |  |  | 8.3 | Percentage of customer enquiries responded to first time against target | Optional - Locally determined | Register of enquiries | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
8 | Community |  |  | 8.4 | Contractors level of engagement with the Scheme communications plan | Optional - Locally determined | Project Manager score | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
8 | Community |  |  | 8.5 | Percentage of targets in communication plan met against number predicted to be achieved | Optional - Locally determined | Achievement of targets set in communication plan | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
9 | Traffic management | To measure the success of minimising the impact of projects on highway users through appropriate traffic management. | Disruption and congestion, all highway users’ considered, appropriate and up to date information for highway users, safety of measures. | 9.1 | Satisfaction against key aspects of traffic management | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
10 | Innovation and Value for Money | To measure the success of innovation through cashable and non-cashable efficiency savings and, demonstrate ongoing value for money. | Continuous improvement through Contractor and supply chain, early Contractor and Supplier involvement, opportunities plan, innovation and value for money. | 10.1 | Innovation Savings as a percentage of initial target price | Core | Innovation Register in place, expressed as the value of Innovations agreed between Project Manager and Contractor as a percentage of initial target price | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme |  | Innovations Register
10 | Innovation and Value for Money |  |  | 10.2 | Satisfaction against key aspects of innovation and value for money | Core | Satisfaction against key aspects | Scheme | Within 4 weeks of the end of scheme | Post package order approval scheme savings register in place and provided to MHA within 4 weeks of end of scheme
10 | Innovation and Value for Money |  |  | 10.3 | CCS Innovation Score | Optional - Locally determined | Latest subsection score out of 5 from CCS visit relating to Innovation | Scheme | Latest score from CCS Monitor visit | The scheme score is based on the most recent CCS report | CCS Score
11 | Commissioning Authority Performance | To measure the approach of the Commissioning Authority in respect of the outcomes established by the MHA |  | 11.1 | Satisfaction against MHA key aspects that provide the right environment to achieve the required outcomes | Core | Satisfaction against key aspects Contractor score | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
11 | Commissioning Authority Performance | To measure the commitment of the Commissioning Authority to support the Contractors to ensure that representatives attending site can do so safety and effectively |  | 11.2 | Percentage of Commissioning Authority representatives attending site (going within the works area requiring PPE) with the appropriate CSCS registration | Core | Details of CSCS registration for Commissioning Authority representatives collated at induction and register maintained by Contractor | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | To ensure Commissioning Authority representatives have appropriate awareness and understanding of Health & Safety in a construction environment. | Expressed as a percentage of total Commissioning Authority representatives attending site with CSC S registration.
11 | Commissioning Authority Performance | To ensure that the Tier 1 Contractors receive prompt payment to facilitate cashflow and demonstrate commitment to the outcomes established by the MHA |  | 11.3 | Tier 1 payments - percentage of payments to Tier 1 Contractors made within 7 days of the assessment date | Core | Percentage of payments to Tier 1 Contractors made within 7 days of the assessment date | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme | To ensure prompt payments to Tier 1 Contractors that facilitates good cash flow | Expressed as a percentage of total Tier 1 payments from payment applications
12 | MHA Framework Community Performance |  |  | 12.1a | Total No. of hours worked on site since construction started | Core | Turnover measure for contractors | Framework | Collected and reported for each Framework Community Board Meeting
|  |  |  | 12.1b | Total No. of hours worked on site in period (since last report). | Core | Turnover measure for contractors | Framework | Collected and reported for each Framework Community Board Meeting
|  |  |  | 12.2a | Number of RIDDORS in period (since last report) | Core |  | Framework | Collected and reported for each Framework Community Board Meeting
|  |  |  | 12.2b | Number of Lost Time Accidents in period (since last report) | Core |  | Framework | Collected and reported for each Framework Community Board Meeting
Reference List
| Yes or No | Yes
No

## 1_Product
Scheme Title | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency
1.1 | Percentage satisfaction against key aspects of product |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
1.1 | Percentage satisfaction against key aspects of product |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
Score | Question 1.1 | Guidance on scores
MHA Multiplier
0 | Totally dissatisfied | More than one key aspect that contributes to a quality product is currently unacceptable to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect that contributes to a quality product is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.6
4 | Dissatisfied | A collection of minor elements of the key aspects that contribute to a quality product are currently unacceptable and outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor elements of the key aspects that contribute to the delivery of a quality product are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the overall quality of the product. | [5 empty] | 0.9
7 | Fairly satisfied | Most of the key aspects that contribute to the delivery of a quality product are satisfactory and these slightly outweigh any minor elements that are currently unacceptable. In general issues that contribute to the delivery of a quality product are being identified by the suppliers own systems and promptly report to the Project Manager. Any minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.95
8 | Satisfied | All key aspects that contribute to a quality product are satisfactory. The majority of issues that contribute to the delivery of a quality product are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate action taken. | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering a quality product are satisfactory. All issues that contribute to the delivery of a quality product are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering a quality product considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. | [5 empty] | 1.1
Key Aspects (examples)
| Construction of main works | Compliance with scheme design
| Handover | Outstanding works at handover
Acceptance inspections and as-built records
| Post project review | Review carried out in a timely manner including performance management information
| Risk register | Kept up to date, reviewed regulaly in line with Early Warning Register
Sustainable construction
Minimise waste creation and maximise recycling
| Opportunities plan | Kept up to date, reviewed regulaly and ongoing dialouge at project meetings
| Work Package Commitments/Promises | Compliance with quality statements relevant to work package made in original framework submission

## 2_Service
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency
2.1 | Satisfaction against key aspects of service |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
2.2 | Supply chain payments - percentage of payments to supply chain made within 7 days of the assessment date |  |  |  | Core | Percentage of payments to supply chain made within 7 days of the assessment date | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
2.1 | Satisfaction against key aspects of service |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
2.2 | Supply chain payments - percentage of payments to supply chain made within 7 days of the assessment date | Complete Scheme Details, cells C60 and C61 |  |  | Core | Percentage of payments to supply chain made within 7 days of the assessment date | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
2.3 | Percentage satisfaction of Tier 2 suppliers with MHA Framework Contractor against MHA standard questionnaire |  |  |  | Optional - Locally determined | Post scheme satisfaction survey carried out by MHA Framework Contractor maximum 4 weeks after completion of scheme. Survey to be developed from framework contractor's existing processes. | Scheme | End of scheme
Comments
Score | Question 2.1 | Guidance on scores
Multiplier
0 | Totally dissatisfied | More than one key aspect that contributes to a quality service is currently unacceptable to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect that contributes to a quality service is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | A collection of minor elements of the key aspects that contribute to a quality service that are currently unacceptable and outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor elements of the key aspects that contribute to a quality service are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the overall service. | [5 empty] | 0.9
7 | Fairly Satisfied | Most of the key aspects that contribute to a quality service are satisfactory and these slightly outweigh any minor elements that are currently unacceptable. In general issues that contribute to the delivery of a quality service are being identified by the suppliers own systems and promptly report to the Project Manager. Any minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.95
8 | Satisfied | All key aspects contribute to a quality service are satisfactory. The majority of issues that contribute to the provision of a quality service are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate action taken. | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering a quality service are satisfactory. All issues that contribute to the delivery of a quality service are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering a quality service considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. | [5 empty] | 1.1
Key Aspects (examples)
| Organisation & management | Works Quality Plan in place pro-actively in advance of work starting to allow review by Project Manager. Appropriate documentation submitted pro-actively and followed e.g. test certificates etc. Quality statements in place sufficiently in advance of activities. Site inductions, task specific training, toolbox talks, briefings include quality. Ensure all people on-site receive and understand project specific quality induction. Pre-start staff competency checks with plant and equipment inspected against quality plan. Regular reviews and checks against framework and site quality KPI’s.
| Procurement of specialists and suppliers | Selection process enables selection of quality subcontractors and suppliers. Supply chain inductions include quality plan. Localism including local small and medium enterprises (SME) involvement and employment.
| Management and improvement of Client relationships | Briefings and feedback include quality, regular quality meetings, quality feedback.
Management and improvement of customer and third party relationships
Innovation and value for money
Management of change
Collaborative working

## 3_Right First Time
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
3.2 | Percentage of disallowed costs due to works not complying with the Scope against adjusted target |  |  |  | Optional - Locally determined |  | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
3.3 | No of NCR's per £100k | Scheme Details - Cells C75 and C84 require completion |  |  | Optional - Locally determined |  | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
3.4 | Percentage of NCR's closed out in the agreed timescale | Scheme Details - Cells C84 and C86 require completion |  |  | Optional - Locally determined |  | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
Score | Question 3.1 | Guidance on scores | [5 empty] | MHA Multiplier
0 | Totally dissatisfied | More than one key aspect that contributes to delivering a product right first time is currently unacceptable to the extent that it calls into question the suppliers capability to deliver a product right first time. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect that contributes to delivering a product right first time is unsatisfactory to the extent that the Project Manager considers that significant intervention is required eg a serious failure of the quality management system resulting in significant additional cost as a result of failure to comply with the Scope. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | A collection of minor elements of the key aspects that contribute to delivering a right first time are currently unacceptable and outweigh those which are satisfactory to the extent that the Project Manager seeks improvement eg failures of the quality management system resulting in additional costs as a result of the failure to comply with the Scope. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor elements of the key aspects that contribute to delivering a right first time are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted . | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the 'right first time' performance. | [5 empty] | 0.9
7 | Fairly satisfied | Most of the key aspects that contribute to delivering a product right first time are satisfactory and these slightly outweigh any minor elements that are currently unacceptable. In general issues that contribute to the delivery of a quality produce are being identified by the suppliers own systems and promptly report to the Project Manager. Any minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.95
8 | Satisfied | All key aspects that contribute to delivering a product right first time are satisfactory. The majority of quality issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1
9 | Very satisfied | All key aspects that contribute to delivering a product right first time are satisfactory. All quality issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause if any issues is promptly investigated and appropriate steps taken. There is a high level of confidence that only a minimal number of minor defects will be outstanding at scheme handover. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects that contribute to delivering a product right first time considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. No defects are outstanding at scheme handover. | [5 empty] | 1.1
Key Aspects
| Mitigating risks through planning | At ECI, review pre-construction information and liaise with Designer to ‘design out’ non conformities. Works Quality Plan in place pro-actively in advance of work starting to allow review. Appropriate documentation submitted pro-actively and followed e.g. test certificates etc. Quality statements in place sufficiently in advance of activities
| Competent people | Site inductions, task specific training, toolbox talks, briefings include quality. Ensure all people on-site receive and understand project specific quality induction. Pre-start staff competency checks with plant and equipment inspected against quality plan.
| Workforce consultation | Briefings and feedback include quality, regular quality meetings, quality feedback
| Continually improving | Process for investigating the cause of defects in place and followed. Process for mitigating impact and ensuring that defects are avoided in the future in place and followed. Quality Audits.
| Supply Chain H & S Management | At ECI identify all 3rd parties and includes discussion on quality. Selection process enables selection of quality subcontractors and suppliers. Supply chain inductions include quality plan.
| Monitoring performance | Regular reviews and checks against framework and site quality KPI’s.
Quality Management System
| MSF3 Quality Charter and Commitments | Proposals are aligned with the requirements of the customers design and specification. Every package of work has an agreed Inspection and Test plan (ITP) and effective checking and verification regime in place. The acceptance criteria for the ITP's meet all the relevant specification, contract and client's requirements. Ensure all exceptions are recorded using a Non Conformance (NCR) process and they contain agreed corrective and preventative actions. NCR's are closed out in an agreed timetable to avoid compromising follow on work which would otherwise be compliant. Measure, record, review and learn from all NCR's and defects throughout the contract, providing customer assurance that quality standards are being achieved. Ensure ambiguities or omissions are highlighted early to avoid unnecessary errors and waste. Maintain essential and sufficient documentation to demonstrate that the product has been installed in a compliant manner. Record and report our quality performance through the Framework Community Board (FCB). Use MSF3 as a conduit for learning and innovation to improve quality and service performance to customers demonstrating the benefits of the collaborative framework.

## 4_Cost management
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score (%) | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency
4.1 | Predictability of cost |  |  |  | Core | Percentage variation of cost against adjusted target price | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
4.2 | Accurately priced compensation events |  |  |  | Core | Percentage variation of cumulative initial value of submitted CE's to the final agreed value of those same events | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
4.1 | Predictability of cost | Complete Scheme Details, cells C74 and C75 |  |  | Core | Percentage variation of cost against adjusted target price | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
4.2 | Accurately priced compensation events | Complete Scheme Details, cells C67 and C68 |  |  | Core | Percentage variation of cumulative initial value of submitted CE's to the final agreed value of those same events | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
4.3 | Percentage of number of compensation events agreed in relation to the number submitted | Complete Scheme Details, cells C70 and C71 |  |  | Optional - Locally determined | From EWN/CE register | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
4.4 | Comparison of budget cost of work to actual cost of work performed (percentage) |  |  |  | Optional - Locally determined | Comparison of budgeted cost of work to actual cost of work performed | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
4.5 | Accuracy of cost and payment records expressed as a percentage |  |  |  | Optional - Locally determined | From audits of submitted cost information | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
| Question 4.1 and 4.2 | MHA Multiplier
For Multiplier see 4_Cost Management Multiplier worksheet

## 5_Time
Scheme Title | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency
5.1 | Percentage satisfaction against key aspects of product |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
Percentage Variance
5.1 | Percentage satisfaction against key aspects of product |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
5.2 | Predictability of time | Complete Scheme details |  |  | Optional - Locally determined | Percentage variation of forecast duration against agreed programme | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
5.3 | Reliability and accuracy of programming of activities |  |  |  | Optional - Locally determined | Programmed activities complete as a percentage of activities due to be complete | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
5.4 | Accuracy of duration for compensation events |  |  |  | Optional - Locally determined | Ratio of agreed cumulative requests (as a percentage) for additional time compared to the submitted periods of those CE's | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
Score | Question 5.1 | Guidance on scores | [5 empty] | MHA Multiplier
0 | Totally dissatisfied | More than one key aspect that contributes to delivering the project on time is currently unacceptable to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect that contributes to delivering the project on time is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | A collection of minor elements of the key aspects that contribute to delivering the project on time are currently unacceptable and outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor elements of the key aspects that contributes to delivering a project on time are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the overall service. | [5 empty] | 0.9
7 | Fairly satisfied | Most of the key aspects that contribute to delivering the project on time are satisfactory and these slightly outweigh any minor elements that are currently unacceptable. In general issues that contribute to the delivery of a project on time are being identified by the suppliers own systems and promptly report to the Project Manager. Any minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.95
8 | Satisfied | All key aspects that contribute to delivering the project on time are satisfactory. The majority of issues that contribute to the provision of delivering the project on time are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate action taken. | [5 empty] | 1
9 | Very satisfied | All key aspects that contribute to delivering the project on time are satisfactory. All issues that contribute to the delivery of the project on time are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects that contribute to delivering the project on time considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. | [5 empty] | 1.1
Key Aspects
| Predict & Forecast | Was it provided with target price. Does it show resources, constraints.
| Monitor & Control | Regular update to programme. Advise on activities, outputs, durations, resources, engineering and traffic management logic and constraints. Mitigate increase in time. Accuracy/time prediction.
| Reporting | Input as built information into Accepted Programme. Produce first and following Programmes for Acceptance. Periodic review and analysis of progress. Adjust and implement future activity outputs and durations. Investigate, identify and implement improvements.

## 6_Safety
Scheme Title | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency
6.1 | Percentage satisfaction against key aspects of safety |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
6.1 | Percentage satisfaction against key aspects of safety |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
Score | Question 6.1 | Guidance on scores | [5 empty] | Multiplier
0 | Totally dissatisfied | More than one key aspect that contributes to health and safety is unsatisfactory to the extent that it calls into question the suppliers capability to continue and deliver the scheme safely. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect that contributes to health and safety is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | A collection of minor elements of the key aspects of health and safety performance are currently unacceptable and outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor elements of the key aspects of health and safety performance are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the health and safety performance. | [5 empty] | 0.9
7 | Fairly satisfied | Most of the key aspects of health and safety performance are satisfactory and these slightly outweigh any minor elements that are currently unacceptable. In general issues that contribute to health and safety are being identified by the suppliers own systems and promptly report to the Project Manager. Any minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.95
8 | Satisfied | All key aspects of health and safety are satisfactory. The agreed commitments and promises made at framework tender stage and individual work package are being met. | [5 empty] | 1
9 | Very satisfied | All key aspects of health and safety are satisfactory and there is evidence that some Health and Safety aspects are exceeding agreed expectations. The supplier is proactive in identifying best practice and can evidence that additional activities are being undertaken which provide a benefit over and above the agreed tender promises at no additional direct cost to the Client. The supplier can evidence that the best practice has been taken up by other suppliers within the MHA Framework. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of health and safety considerably exceed expectations with active monitoring of their own and, the supply chain arrangements. The scheme may have received an award from a recognised body for health and safety management. The supplier can evidence work undertaken without an increase to the cost of the work package and, which has been deployed on other schemes, suppliers within and outside the MHA Framework. | [5 empty] | 1.1
Key Aspects
| Mitigating risks through planning | At ECI, review pre-construction information and liaise with Principal Designer / Designer's to ‘design out’ high risk activities. H&S Plan in place pro-actively in advance of work starting to allow review. Appropriate documentation eg method statements submitted pro-actively and followed e.g. risk assessment, method statements.
| Workforce | Pre-employment assessment, site inductions, task specific training, toolbox talks, method statement briefings. Briefings and feedback, regular safety committee meetings, welfare surveys, training feedback. Welfare facilities compliant with Construction Design and Management Regulations 2015.
| Continually improving | Reviews near misses/accidents/incidents with HSEQ Manager.
| Supply Chain H & S Management | At ECI identify all 3rd parties and set-up communication channels. Pre-start safety meetings, toolbox talks, regular safety meetings, sub contractor operatives fully briefed on Method Statements and Risk Assessments.
| Monitoring performance | Regular reviews and project health checks against framework and site KPI’s.
| Effectiveness of safety system | Near misses.

## 7_Social Value
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency
7.1 | Contractors engagement in the Employment and Skills Plan |  |  |  | Core | Satisfaction against level of engagement, approach and likelihood of achieving targets. | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
7.2 | Percentage of ESP activities where agreed targets set have been achieved |  |  |  | Core | Achievement of agreed targets set in the ESP measured on an activity level | Scheme | End of scheme
Scores | Measure | Score
7.1 | Contractors engagement in the Employment and Skills Plan |  |  |  | Core | Satisfaction against level of engagement, approach and likelihood of achieving targets. | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
7.2 | Percentage of ESP activities where agreed targets set have been achieved |  |  |  | Core | Achievement of agreed targets set in the ESP measured on an activity level | Scheme | End of scheme
7.3 | Building Social Value Assessment | Not Applicable - report used for shared learning through Framework Community Board |  |  | Report is a Framework Requirement | Building Social Value Inspection Report at end of scheme | Scheme | End of scheme
Comments
Score | Question 7.1 | Guidance on scores | [5 empty] | Multiplier
0 | Totally dissatisfied | The Contractor is not engaging with the ESP or working towards targets set-out and it is highly likely that none of the targets will not be met. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | The Contractor is not engaging with the ESP or working towards targets set-out and it is highly likely that most of the targets will not be met. The Project Manager will have written to the suppliers ramework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | The Contractor is not engaging with the ESP or working towards targets set-out and it is likely that some targets will not be met to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board | [5 empty] | 0.7
5 | Slightly dissatisfied | The Contractor is engaging with the ESP but progress against targets targets is slow to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting and the Contractor is willing and working proactively to improve. | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the level of engagement with the ESP or progrress working towards targets set-out. | [5 empty] | 0.9
7 | Fairly satisified | The Contractor is engaging with the ESP and working towards achieving the targets set-out in the ESP but difficulties are being encountered that means target may not be met. The ESP is a standing item on the agenda of progress meetings and the Project Manager is kept up to date on plans being considered and the Contractor is being proactive in improving performance, | [5 empty] | 0.95
8 | Satisfied | The Contractor is engaging with the ESP and working towards achieving the targets set-out in the ESP and it is likely that these will or have been met. The ESP is a standing item on the agenda of progress meetings and the Project Manager is kept up to date on plans being considered. | [5 empty] | 1
9 | Very satisfied | The Contractor is proactively and positvely engaging with the ESP to achieve and exceed the targets set-out in the ESP and it is likely that these will or have been met. The ESP is a standing item on the agenda and an integral part of the outputs related to project delivery. | [5 empty] | 1.05
10 | Exceptionally satisfied | The Contractor is proactively and positvely engaging with the ESP and working in a collaborative manner with the Client, Suppliers and Sub-Contractors to achieve and exceed the targets set-out in the ESP and it is likely that these will or have been met. The ESP is a standing item on the agenda and an integral part of the outputs related to project delivery. Positive communication is being received and progress is being actively promoted within the local area, through the client and Framework Community Board. | [5 empty] | 1.1
| Question 7.2 | MHA Multiplier
See Worksheet 7_Social Value Calculation

## 8_Community
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency
8.1 | Considerate Constructors Score (CCS) |  |  |  | Core | Considerate Constructors Scheme Inspection | Scheme | Latest score from CCS Monitor visit
Scores | Measure | Score
8.1 | Considerate Constructors Score (CCS) |  |  |  | Core | Considerate Constructors Scheme Inspection | Scheme | Latest score from CCS Monitor visit
8.1a | CCS - (1) Care about appearance |  |  |  | Info Only | Considerate Construction Scheme Inspection | Scheme | Latest subsection score from CCS Monitor visit
8.1b | CCS - (2) Respect the community
8.1c | CCS - (3) Protect the environment
8.1d | CCS - (4) Secure everyone's safety
8.1d | CCS - (5) Value the workforce
8.2 | Overall satisfaction with construction of the works (percentage) |  |  |  | Optional - Locally determined | Frontage scheme and stakeholder satisfaction survey | Scheme | End of scheme
8.3 | Percentage of customer enquiries responded to first time against target |  |  |  | Optional - Locally determined | Register of enquiries | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
8.4 | Contractors level of engagement with the Scheme communications plan |  |  |  | Optional - Locally determined | Project Manager score | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
8.5 | Percentage of targets in communication plan met against number predicted to be achieved |  |  |  | Optional - Locally determined | Achievement of targets set in communication plan | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
| Question 8.1 | MHA Multiplier
See Worksheet 8_Community Score Calculation

## 9_Traffic Management
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency
9.1 | Satisfaction against key aspects of traffic management |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Scores | Measure | Score
9.1 | Satisfaction against key aspects of traffic management |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
Comments
Score | Questions 9.1 | Guidance for scoring | [5 empty] | MHA Multiplier
0 | Totally dissatisfied | More than one key aspect that contributes to delivering an effective the traffic management system is currently unacceptable to the extent that it calls into question the suppliers capability to deliver traffic management. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect that contributes to delivering an effective traffic management system is unsatisfactory to the extent that the Project Manager considers that significant intervention is required eg a serious failure of the traffic management system resulting in significant actual or reputational issues such as failure to comply with Chapter 8 of the Traffic Signs Manual. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | A collection of minor elements of the key aspects that contribute to delivering an effective traffic management system being used are unacceptable and outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points. Dissatisfied scores will be discussed at Framework Community Board. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor aspects of the key aspects that contribute to delivering n effective traffic management system are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The minor aspects unacceptable are being discussed proactively between the project team at progress meetings with actions minuted . | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the traffic management systems. | [5 empty] | 0.9
7 | Fairly satisfied | Most of the key aspects of delivering an effective traffic management system are satisfactory and these slightly outweigh any minor elements that are currently unacceptable. In general issues that contribute to the traffic management system are being identified by the suppliers own systems and promptly report to the Project Manager. Any minor elements unacceptable are being discussed proactively between the project team at progress meetings with actions minuted. | [5 empty] | 0.95
8 | Satisfied | All key aspects of the traffic management system are satisfactory. The majority of issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering traffic management right first time are satisfactory. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause if any issues is promptly investigated and appropriate steps taken. There is a minimal number of issues in relation to traffic management being reported by highway users. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering traffic management considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. The number of compliments received for traffic management exceeds the number of complaints. | [5 empty] | 1.1
Key Aspects
Disruption and congestion minimised
All highway users considered
Appropriate and up to date information through a variety of media
Safety of measures
Maintenance of signing including diversion routes
Removal of temporary signing when no longer required

## 10_Innovation & Value for Money
Scheme Title | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency
10.1 | Innovation Savings as a percentage of initial target price |  |  |  | Core | Innovation Register in place and supplied to MHA within 4 weeks of the end of scheme, expressed as the value of Innovation Savings as a percentage of intial target price | Scheme | Within 4 weeks of the end of scheme
10.2 | Satisfaction against key aspects that provide the right environment for innovation and value for money |  |  |  | Core | Satisfaction against key aspects | Scheme | Every six months
Scores | Measure | Score
10.1 | Innovation Savings as a percentage of initial target price | Complete scheme details, cells C64 and C77 |  |  | Core | Innovation Register in place and supplied to MHA within 4 weeks of the end of scheme, expressed as the value of Innovation Savings as a percentage of intial target price | Scheme | Within 4 weeks of the end of scheme
10.2 | Satisfaction against key aspects of innovation and value for money |  |  |  | Core | Satisfaction against key aspects | Scheme | Within 4 weeks of the end of scheme
10.3 | CCS Innovation Score |  |  |  | Optional - Locally determined | Latest subsection score out of 5 from CCS visit relating to Innovation | Scheme | Latest score from CCS Monitor visit
Comments
| Question 10.1 | MHA Multiplier
See Worksheet 10_ECI Savings Multiplier
Score | Question 10.2 | Guidance on scoring | [5 empty] | Multipler
0 | Totally dissatisfied | No commitment to innovate. The Project Manager will have written to the suppliers Director and the MHA Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | The Contractor has developed a savings / innovations / opportunities register but few opportunities have been identifed and delivered. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board. | [5 empty] | 0.6
4 | Dissatisfied | Most aspects of the development of the savings / innovations / opportunties register are unacceptable and outweigh those which are satisfactory to the extent that the Project Manager sought improvement, but limited action was taken by the Contractor. | [5 empty] | 0.7
5 | Slightly dissatisfied | Some minor aspects of the development of the savings / innovations / opportunties register are unacceptable and outweigh those which are satisfactory to the extent that the Project Manager sought improvement, but following investigation the nature of the scheme shown oppurtunities to be limited. | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The savings/innovations/opportunities register been developed but, the Project Manager is neither satisfied or dissatisfied with the willingness to innovate and demonstrate value for money | [5 empty] | 0.9
7 | Fairly satisified | The Contractor demostrates a commitment to developing the savings / innovations / oppurtunities register and implements some of the aspects identified. | [5 empty] | 0.95
8 | Satisfied | The Contractor demonstrates an adequate commitment to developing the savings/innovations/opportunities register in line with the commitments made at Framework Tender Stage and, individual work package requirements. | [5 empty] | 1
9 | Very satisfied | The Contractor demonstrates an good commitment to developing the savings/innovations/opportunities register and successfully implements most of the aspects identified and shares the success with the Framework Community | [5 empty] | 1.05
10 | Exceptionally satisfied | The Contractor demonstrates an excellent commitment to developing the savings/innovations/opportunities register implements the aspects identified and captures and shares the success with the Framework Community. | [5 empty] | 1.1
Key Aspects
Ongoing Contractor and Supplier involvement
Opportunities plan
Pull value and innovation up through supply chain
Culture

## 11_Commissioning Authority
Scheme Title | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score |  | Type | Method | Applies to | Frequency
11.1 | Satisfaction against MHA key aspects that provide the right environment to achieve the required outcomes | 6 |  | Core | Satisfaction against key aspects Contractor score | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
11.2 | Percentage of Commissioning Authority representatives attending site (going within the works area requiring PPE) with the appropriate CSCS registration |  |  | Core | Details of CSCS registration for Commissioning Authority representatives collated at induction and register maintained by Contractor | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
11.3 | Tier 1 payments - percentage of payments to Tier 1 Contractors made within 7 days of the assessment date |  |  | Core | Percentage of payments to Tier 1 Contractors made within 7 days of the assessment date | Scheme | In Project - Monthly intervals & Within 4 weeks of the end of scheme
To help understand performance different than that expected through the Framework, please provide comments below
Comments
Score | Question 11.1
0 | Totally dissatisfied | No commitment to achieve the outcomes of the MHA. The Contractors Framework Manager will have written to the Commissioning Authority and the MHA Manager.
2 | Very dissatisfied | The Commissioning Authority has managed the Works Package but with limited reference to the outcomes of the MHA. The Contractors Framework Manager will have written to the Commissioning Authority and the MHA Manager. Client not engaged with Performance Toolkit, Toolkit not in use.
4 | Dissatisfied | Limited aspects of Commissioning Authority approach towards achieving the outcomes of the MHA have been implemented and do not outweighed by those which are absent. Client not engaged with Performance Toolkit which is not regulary used.
5 | Slightly dissatisfied | Some aspects of Commissioning Authority approach towards achieving the outcomes of the MHA have been implemented but are generally outweighed by those which are absent. Client not engaged with Performance Toolkit which is not regulary used.
6 | Neither satisfied or dissatisfied | The Contractor is neither satisfied or dissatisfied with the willingness to achieve the outcomes of the MHA. This options should only be chosen following consultation with the MHA Framework Manager. Client not fully engaged with use of Performance Toolkit.
7 | Fairly Satisfied | The Commissioning Authority worked within the outcomes of the MHA in line with the Framework Information and individual work package requirements, but had to be prompted regularly to fully engage in the use of Performance Toolkit and regularly submitted.
8 | Satisfied | The Commissioning Authority demonstrates a commitment to achieving the outcomes of the MHA in line with the Framework Information and individual work package requirements. Client fully engaged in use of Performance Toolkit and regularly submitted.
9 | Very satisfied | The Commissioning Authority demonstrates an good commitment to achieving the outcomes of the MHA and shares the success with the Framework Community. Client fully engaged with use of Performance Toolkit, jointly agreed, regularly submitted, optional measures in use, good practice being captured and shared in case studies.
10 | Exceptionally satisfied | The Commissioning Authority demonstrates an excellent commitment to achieving the outcomes of the MHA in all aspects and captures and shares the success with the Framework Community. Client fully engaged with use of Performance Toolkit which is regularly submitted, good practice being captured and shared in case studies with development of optional measures.
Key Aspects
Clarity of instructions received
Quality/clarity of feedback
Clarity of client's roles and responsibilities
Flexibility and responsiveness
Liaison
Communications of change
Friendly but business-like;
Proactive rather than reactive;
Flexible, where all parties are prepared to change;
Respectful of differences;
Risk is appropriately proportioned;
Act in a spirit of openness and trust;
Act to secure best value for money and continuous improvement;
Objectives are shared with long-term commitment from all parties by establishing an effective joint management and decision-making structure;
Enables innovation and implements change in a timely manner
So far as possible, avoid conflicts or disagreements and, should they arise, will resolve them promptly together.
Use of Performance Management Toolkit;
Proactive in working with Contractor to close off and agree Compensation Events and Clause 32 programme.

## Stage 1 Scheme Scores
Scheme Title | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0
| Scheme Score |  |  | Latest MHA Score | Latest Score
|  |  |  | 0 | 0
Measure
X22.1 | Satisfaction against key aspects of service |  |  | 0 | 0
X22.2 | Satisfaction against key aspects of product |  |  | 0 | 0
X22.3 | Satisfaction against key aspects of value for money |  |  | 0 | 0
X22.4 | Satisfaction against key aspects of provision of cost information |  |  | 0 | 0
X22.5 | Predictability to Time for Stage 0 - % change of time to enter Stage 1 |  |  | Complete Scheme Details at end of Stage 1 | Complete Scheme Details at end of Stage 1
X22.6 | Innovation Savings as a percentage of initial target price |  |  | Please complete Scheme Details | Please complete Scheme Details
X22.7 | Predictability to Time for Stage 1 - % change of time to complete Stage 1 |  |  | Please complete Scheme Details | Please complete Scheme Details
X22.8 | Predictability to Cost for Stage 1 - % change of forecast to actual cost |  |  | Please complete Scheme Details | Please complete Scheme Details
X22.9 | Predictability to Cost - % change of Budget |  |  | Please complete Scheme Details | Please complete Scheme Details
X22.10 | Predictability to Cost - % change of Works Costs |  |  | Please complete Scheme Details | Please complete Scheme Details
Formulas:
Latest Score = [Latest MHA Score]

## Stage 2 Scheme Scores
Scheme Title | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0
| Scheme Score |  |  | Latest MHA Score | Latest Score
|  |  |  | 0 | 0
1 | Product
1.1 | Percentage satisfaction against key aspects of product | Core
2 | Service
2.1 | Satisfaction against key aspects of service | Core
2.2 | Supply chain payments - percentage of payments to supply chain made within 7 days of the assessment date | Core
3 | Right first time
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction | Core
4 | Cost management
4.1 | Predictability of cost | Core
4.2 | Accurately priced compensation events | Core
5 | Time
5.1 | Percentage satisfaction against key aspects of product | Core
6 | Safety
6.1 | Percentage satisfaction against key aspects of safety | Core
7 | Social Value
7.1 | Contractors engagement in the Employment and Skills Plan | Core
7.2 | Percentage of ESP activities where agreed targets set have been achieved | Core
8 | Community
8.1 | Considerate Constructors Score (CCS) | Core
9 | Traffic management
9.1 | Satisfaction against key aspects of traffic management | Core
10 | Innovation and Value for Money
10.1 | Innovation Savings as a percentage of initial target price | Core
10.2 | Satisfaction against key aspects of innovation and value for money | Core
11 | Commissioning Authority Performance
11.1 | Satisfaction against MHA key aspects that provide the right environment to achieve the required outcomes | Core |  | 6 | 6
11.2 | Percentage of Commissioning Authority representatives attending site (going within the works area requiring PPE) with the appropriate CSCS registration | Core |  | 0 | 0
11.3 | Tier 1 payments - percentage of payments to Tier 1 Contractors made within 7 days of the assessment date | Core |  | 0 | 0
| MHA Multiplier |  | Rolling MHA Multiplier for Scheme | Latest MHA Multiplier for Scheme | Latest Score
|  |  |  | From | From
1 | Product
1.1 | Percentage satisfaction against key aspects of product | Core | #DIV/0!
2 | Service
2.1 | Satisfaction against key aspects of service | Core | #DIV/0!
2.2 | Supply chain payments - percentage of payments to supply chain made within 7 days of the assessment date | Core | #DIV/0!
3 | Right first time
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction | Core | #DIV/0!
4 | Cost management
4.1 | Predictability of cost | Core | #DIV/0!
4.2 | Accurately priced compensation events | Core | #DIV/0!
5 | Time
5.1 | Percentage satisfaction against key aspects of product | Core | #DIV/0!
6 | Safety
6.1 | Percentage satisfaction against key aspects of safety | Core | #DIV/0!
7 | Social Value
7.1 | Contractors engagement in the Employment and Skills Plan | Core | #DIV/0!
7.2 | Percentage of ESP activities where agreed targets set have been achieved | Core | #DIV/0!
8 | Community
8.1 | Considerate Constructors Score (CCS) | Core | #DIV/0!
9 | Traffic management
9.1 | Satisfaction against key aspects of traffic management | Core | #DIV/0!
10 | Innovation and Value for Money
10.1 | Innovation Savings as a percentage of initial target price | Core | #DIV/0!
10.2 | Satisfaction against key aspects of innovation and value for money | Core | #DIV/0!
Formulas:
Latest Score = [Latest MHA Score]

## Stage 2 Scheme Scores - Charts
Scheme Title | 0
Contractor | 0
Period | 0
MHA Ref | 0
Commissioning Authority | 0

## Stage 2 Optional Scheme Scores
Scheme Title | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0
| Optional Scheme Score |  |  | Latest MHA Score | Latest Score
|  |  |  | 0 | 2016-01-01
1 | Product
2 | Service
2.3 | Percentage satisfaction of Tier 2 suppliers with MHA Framework Contractor against MHA standard questionnaire | Optional - Locally determined |  | 0 | 0
3 | Right first time
3.2 | Percentage of disallowed costs due to works not complying with the Scope against adjusted target | Optional - Locally determined |  | 0 | 0
3.3 | No of NCR's per £100k | Optional - Locally determined |  | Scheme Details - Cells C75 and C84 require completion | Scheme Details - Cells C75 and C84 require completion
3.4 | Percentage of NCR's closed out in the agreed timescale | Optional - Locally determined |  | Scheme Details - Cells C84 and C86 require completion | Scheme Details - Cells C84 and C86 require completion
4 | Cost management
4.3 | Percentage of number of compensation events agreed in relation to the number submitted | Optional - Locally determined |  | Complete Scheme Details, cells C70 and C71 | Complete Scheme Details, cells C70 and C71
4.4 | Comparison of budget cost of work to actual cost of work performed (percentage) | Optional - Locally determined |  | 0 | 0
4.5 | Accuracy of cost and payment records expressed as a percentage | Optional - Locally determined |  | 0 | 0
5 | Time
5.2 | Predictability of time | Optional - Locally determined |  | Complete Scheme details | Complete Scheme details
5.3 | Reliability and accuracy of programming of activities | Optional - Locally determined |  | 0 | 0
5.4 | Accuracy of duration for compensation events | Optional - Locally determined |  | 0 | 0
6 | Safety
7 | Learning and development
8 | Community
8.2 | Overall satisfaction with construction of the works (percentage) | Optional - Locally determined |  | 0 | 0
8.3 | Percentage of customer enquiries responded to first time against target | Optional - Locally determined |  | 0 | 0
8.4 | Contractors level of engagement with the Scheme communications plan | Optional - Locally determined |  | 0 | 0
8.5 | Percentage of targets in communication plan met against number predicted to be achieved | Optional - Locally determined |  | 0 | 0
9 | Traffic management
10 | Innovation and quality for money
10.3 | CCS Innovation Score | Optional - Locally determined |  | 0 | 0

## Optional Scheme Scores - Charts
Scheme Name | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0

## 2_Service Multiplier
Supply chain payments - percentage of payments to supply chain made within 7 days of the assessment date
% | MHA Score | MHA Multiplier
100 | 10 | 1.1 | Exceptionally satisfied
99 | 9 | 1.05 | Very satisfied
98 | 9 | 1.05
97 | 9 | 1.05
96 | 9 | 1.05
95 | 9 | 1.05
94 | 8 | 1 | Satisfied
93 | 8 | 1
92 | 8 | 1
91 | 8 | 1
90 | 8 | 1
89 | 6 | 0.9 | Neither satisfied or dissatisfied
88 | 6 | 0.9
87 | 6 | 0.9
86 | 6 | 0.9
85 | 6 | 0.9
84 | 5 | 0.8 | Slightly dissatisfied
83 | 5 | 0.8
82 | 5 | 0.8
81 | 5 | 0.8
80 | 5 | 0.8
79 | 5 | 0.8
78 | 5 | 0.8
77 | 5 | 0.8
76 | 5 | 0.8
75 | 5 | 0.8
74 | 5 | 0.8
73 | 5 | 0.8
72 | 5 | 0.8
71 | 5 | 0.8
70 | 5 | 0.8
69 | 2 | 0.6 | Very dissatisfied
68 | 2 | 0.6
67 | 2 | 0.6
66 | 2 | 0.6
65 | 2 | 0.6
64 | 2 | 0.6
63 | 2 | 0.6
62 | 2 | 0.6
61 | 2 | 0.6
60 | 2 | 0.6
59 | 0 | 0.5 | Totally dissatisfied
58 | 0 | 0.5
57 | 0 | 0.5
56 | 0 | 0.5
55 | 0 | 0.5
54 | 0 | 0.5
53 | 0 | 0.5
52 | 0 | 0.5
51 | 0 | 0.5
50 | 0 | 0.5
49 | 0 | 0.5
48 | 0 | 0.5
47 | 0 | 0.5
46 | 0 | 0.5
45 | 0 | 0.5
44 | 0 | 0.5
43 | 0 | 0.5
42 | 0 | 0.5
41 | 0 | 0.5
40 | 0 | 0.5
39 | 0 | 0.5
38 | 0 | 0.5
37 | 0 | 0.5
36 | 0 | 0.5
35 | 0 | 0.5
34 | 0 | 0.5
33 | 0 | 0.5
32 | 0 | 0.5
31 | 0 | 0.5
30 | 0 | 0.5
29 | 0 | 0.5
28 | 0 | 0.5
27 | 0 | 0.5
26 | 0 | 0.5
25 | 0 | 0.5
24 | 0 | 0.5
23 | 0 | 0.5
22 | 0 | 0.5
21 | 0 | 0.5
20 | 0 | 0.5
19 | 0 | 0.5
18 | 0 | 0.5
17 | 0 | 0.5
16 | 0 | 0.5
15 | 0 | 0.5
14 | 0 | 0.5
13 | 0 | 0.5
12 | 0 | 0.5
11 | 0 | 0.5
10 | 0 | 0.5
9 | 0 | 0.5
8 | 0 | 0.5
7 | 0 | 0.5
6 | 0 | 0.5
5 | 0 | 0.5
4 | 0 | 0.5
3 | 0 | 0.5
2 | 0 | 0.5
1 | 0 | 0.5
0 | 0 | 0.5

## 4_Cost Management Muliplier
4.1 PREDICTABILITY OF COSTS |  |  |  | % priced compensation events
% Variance | MHA Score | MHA Multiplier |  | % Agreed | MHA Score | MHA Multiplier
Less than or equal to -40% | 10 | 1.1 | 30% Contractor/70% Client | Less than -50 | 0 | 0.5 | Totally Dissatisfied
39 |  |  |  | -50 | 2 | 0.6 | Very Dissatisfied
-38 | 10 | 1.1 |  | -49 | 2 | 0.6
-37 | 10 | 1.1 |  | -48 | 2 | 0.6
-36 | 10 | 1.1 |  | -47 | 2 | 0.6
-35 | 10 | 1.1 |  | -46 | 2 | 0.6
-34 | 10 | 1.1 |  | -45 | 2 | 0.6
-33 | 10 | 1.1 |  | -44 | 2 | 0.6
-32 | 10 | 1.1 |  | -43 | 2 | 0.6
-31 | 10 | 1.1 |  | -42 | 2 | 0.6
-30 | 10 | 1.1 |  | -41 | 2 | 0.6
-29 | 10 | 1.1 |  | -40 | 5 | 0.8 | Slightly Dissatisfied
-28 | 10 | 1.1 |  | -39 | 5 | 0.8
-27 | 10 | 1.1 |  | -38 | 5 | 0.8
-26 | 10 | 1.1 |  | -37 | 5 | 0.8
-25 | 10 | 1.1 |  | -36 | 5 | 0.8
-24 | 10 | 1.1 |  | -35 | 5 | 0.8
-23 | 10 | 1.1 |  | -34 | 5 | 0.8
-22 | 10 | 1.1 |  | -33 | 5 | 0.8
-21 | 10 | 1.1 |  | -32 | 5 | 0.8
-20 | 9 | 1.05 | 50% Contractor/50% Client Share | -31 | 5 | 0.8
-19 |  |  |  | -30 | 5 | 0.8
-18 | 9 | 1.05 |  | -29 | 5 | 0.8
-17 | 9 | 1.05 |  | -28 | 5 | 0.8
-16 | 9 | 1.05 |  | -27 | 5 | 0.8
-15 | 9 | 1.05 |  | -26 | 5 | 0.8
-14 | 9 | 1.05 |  | -25 | 6 | 0.9 | Neither Satisfied or Dissatisfied
-13 | 9 | 1.05 |  | -24 | 6 | 0.9
-12 | 9 | 1.05 |  | -23 | 6 | 0.9
-11 | 9 | 1.05 |  | -22 | 6 | 0.9
-10 | 9 | 1.05 |  | -21 | 6 | 0.9
-9 | 9 | 1.05 |  | -20 | 6 | 0.9
-8 | 9 | 1.05 |  | -19 | 6 | 0.9
-7 | 9 | 1.05 |  | -18 | 6 | 0.9
-6 | 9 | 1.05 |  | -17 | 6 | 0.9
-5 | 9 | 1.05 |  | -16 | 6 | 0.9
-4 | 9 | 1.05 |  | -15 | 7 | 0.95 | Fairly Satisfied
-3 | 8 | 1 |  | -14 | 7 | 0.95
-2 | 8 | 1 |  | -13 | 7 | 0.95
-1 | 8 | 1 |  | -12 | 7 | 0.95
0 | 8 | 1 |  | -11 | 7 | 0.95
1 | 8 | 1 |  | -10 | 8 | 1 | Satisfied
2 | 8 | 1 |  | -9 | 8 | 1
3 | 8 | 1 |  | -8 | 8 | 1
4 | 5 | 0.8 |  | -7 | 8 | 1
5 | 5 | 0.8 |  | -6 | 8 | 1
6 | 5 | 0.8 |  | -5 | 9 | 1.05 | Very Satisfied
7 | 5 | 0.8 |  | -4 | 9 | 1.05
8 | 5 | 0.8 |  | -3 | 9 | 1.05
9 | 5 | 0.8 |  | -2 | 10 | 1.1 | Exceptionally satisfied
10 | 5 | 0.8 |  | -1 | 10 | 1.1
11 | 2 | 0.6 | Contractor 100%/Client 0% Share | 0 | 10 | 1.1
12 | 2 | 0.6 |  | 1 | 10 | 1.1
13 | 2 | 0.6 |  | 2 | 10 | 1.1
14 | 2 | 0.6 |  | 3 | 9 | 1.05 | Very Satisfied
15 | 2 | 0.6 |  | 4 | 9 | 1.05
16 | 2 | 0.6 |  | 5 | 9 | 1.05
17 | 2 | 0.6 |  | 6 | 8 | 1 | Satisfied
18 | 2 | 0.6 |  | 7 | 8 | 1
19 | 2 | 0.6 |  | 8 | 8 | 1
20 | 2 | 0.6 |  | 9 | 8 | 1
21 | 0 | 0.5 |  | 10 | 8 | 1
22 | 0 | 0.5 |  | 11 | 7 | 0.95 | Fairly Satisfied
23 | 0 | 0.5 |  | 12 | 7 | 0.95
24 | 0 | 0.5 |  | 13 | 7 | 0.95
25 | 0 | 0.5 |  | 14 | 7 | 0.95
26 | 0 | 0.5 |  | 15 | 7 | 0.95
27 | 0 | 0.5 |  | 16 | 6 | 0.9 | Neither Satisfied or Dissatisfied
28 | 0 | 0.5 |  | 17 | 6 | 0.9
29 | 0 | 0.5 |  | 18 | 6 | 0.9
30 | 0 | 0.5 |  | 19 | 6 | 0.9
Greater than or equal to 31% | 0 | 0.5 |  | 20 | 6 | 0.9
|  |  |  | 21 | 6 | 0.9
|  |  |  | 22 | 6 | 0.9
|  |  |  | 23 | 6 | 0.9
|  |  |  | 24 | 6 | 0.9
|  |  |  | 25 | 6 | 0.9
|  |  |  | 26 | 5 | 0.8 | Slightly Dissatisfied
|  |  |  | 27 | 5 | 0.8
|  |  |  | 28 | 5 | 0.8
|  |  |  | 29 | 5 | 0.8
|  |  |  | 30 | 5 | 0.8
|  |  |  | 31 | 5 | 0.8
|  |  |  | 32 | 5 | 0.8
|  |  |  | 33 | 5 | 0.8
|  |  |  | 34 | 5 | 0.8
|  |  |  | 35 | 5 | 0.8
|  |  |  | 36 | 5 | 0.8
|  |  |  | 37 | 5 | 0.8
|  |  |  | 38 | 5 | 0.8
|  |  |  | 39 | 5 | 0.8
|  |  |  | 40 | 5 | 0.8
|  |  |  | 41 | 2 | 0.6 | Very Dissatisfied
|  |  |  | 42 | 2 | 0.6
|  |  |  | 43 | 2 | 0.6
|  |  |  | 44 | 2 | 0.6
|  |  |  | 45 | 2 | 0.6
|  |  |  | 46 | 2 | 0.6
|  |  |  | 47 | 2 | 0.6
|  |  |  | 48 | 2 | 0.6
|  |  |  | 49 | 2 | 0.6
|  |  |  | 50 | 2 | 0.6
|  |  |  | Greater than 50% | 0 | 0.5 | Totally Dissatisfied

## 7_Social Value Calculation
% ESP activites where agreed targets set have been achieved | MHA Score | MHA Multiplier
100 | 10 | 1.1 | Exceptionally satisfied
99 | 9 | 1.05 | Very satisfied
98 | 9 | 1.05
97 | 9 | 1.05
96 | 9 | 1.05
95 | 9 | 1.05
94 | 8 | 1 | Satisfied
93 | 8 | 1
92 | 8 | 1
91 | 8 | 1
90 | 8 | 1
89 | 8 | 1
88 | 8 | 1
87 | 8 | 1
86 | 8 | 1
85 | 8 | 1
84 | 8 | 1
83 | 8 | 1
82 | 8 | 1
81 | 8 | 1
80 | 8 | 1
79 | 7 | 0.95 | Fairly Satisfied
78 | 7 | 0.95
77 | 7 | 0.95
76 | 7 | 0.95
75 | 7 | 0.95
74 | 7 | 0.95
73 | 7 | 0.95
72 | 7 | 0.95
71 | 7 | 0.95
70 | 7 | 0.95
69 | 6 | 0.9 | Neither satisfied or dissatisfied
68 | 6 | 0.9
67 | 6 | 0.9
66 | 6 | 0.9
65 | 6 | 0.9
64 | 6 | 0.9
63 | 6 | 0.9
62 | 6 | 0.9
61 | 6 | 0.9
60 | 6 | 0.9
59 | 5 | 0.8 | Slightly dissatisfied
58 | 5 | 0.8
57 | 5 | 0.8
56 | 5 | 0.8
55 | 5 | 0.8
54 | 5 | 0.8
53 | 5 | 0.8
52 | 5 | 0.8
51 | 5 | 0.8
50 | 5 | 0.8
49 | 4 | 0.7 | Dissatisfied
48 | 4 | 0.7
47 | 4 | 0.7
46 | 4 | 0.7
45 | 4 | 0.7
44 | 4 | 0.7
43 | 4 | 0.7
42 | 4 | 0.7
41 | 4 | 0.7
40 | 4 | 0.7
39 | 2 | 0.6 | Very dissatisfied
38 | 2 | 0.6
37 | 2 | 0.6
36 | 2 | 0.6
35 | 2 | 0.6
34 | 2 | 0.6
33 | 2 | 0.6
32 | 2 | 0.6
31 | 2 | 0.6
30 | 2 | 0.6
29 | 0 | 0.5 | Totally dissatisfied
28 | 0 | 0.5
27 | 0 | 0.5
26 | 0 | 0.5
25 | 0 | 0.5
24 | 0 | 0.5
23 | 0 | 0.5
22 | 0 | 0.5
21 | 0 | 0.5
20 | 0 | 0.5
19 | 0 | 0.5
18 | 0 | 0.5
17 | 0 | 0.5
16 | 0 | 0.5
15 | 0 | 0.5
14 | 0 | 0.5
13 | 0 | 0.5
12 | 0 | 0.5
11 | 0 | 0.5
10 | 0 | 0.5
9 | 0 | 0.5
8 | 0 | 0.5
7 | 0 | 0.5
6 | 0 | 0.5
5 | 0 | 0.5
4 | 0 | 0.5
3 | 0 | 0.5
2 | 0 | 0.5
1 | 0 | 0.5
0 | 0 | 0.5

## 8_Community Score Calculation
CCS Score | MHA Score | MHA Multiplier
1 | 0 | 0.5 | Totally dissatisfied
2 | 0 | 0.5
3 | 0 | 0.5
4 | 0 | 0.5
5 | 0 | 0.5
6 | 0 | 0.5
7 | 0 | 0.5
8 | 0 | 0.5
9 | 0 | 0.5
10 | 0 | 0.5
11 | 0 | 0.5
12 | 0 | 0.5
13 | 0 | 0.5
14 | 0 | 0.5
15 | 0 | 0.5
16 | 0 | 0.5
17 | 0 | 0.5
18 | 0 | 0.5
19 | 0 | 0.5
20 | 0 | 0.5
21 | 0 | 0.5
22 | 0 | 0.5
23 | 0 | 0.5
24 | 0 | 0.5
25 | 2 | 0.6 | Very dissatisfied
26 | 4 | 0.7 | Slighty dissatisfied
27 | 4 | 0.7
28 | 4 | 0.7
29 | 4 | 0.7
30 | 6 | 0.9
31 | 6 | 0.9
32 | 6 | 0.9
33 | 6 | 0.9
34 | 6 | 0.9 | Neither
35 | 8 | 1 | Satisfied | CCS Average Score
36 | 8 | 1
37 | 8 | 1
38 | 8 | 1
39 | 8 | 1
40 | 9 | 1.05 | Very satisfied
41 | 9 | 1.05
42 | 9 | 1.05
43 | 9 | 1.05
44 | 9 | 1.05
45 | 10 | 1.05 | Exceptionally satisfied
46 | 10 | 1.1
47 | 10 | 1.1
48 | 10 | 1.1
49 | 10 | 1.1
50 | 10 | 1.1

## 10_Savings Multiplier
% Saving | MHA Score | MHA Multiplier
0% | 5 | 0.8 | Slightly dissatisfied
1% | 5 | 0.8
2% | 8 | 1 | Satisfied
3% | 8 | 1
4% | 8 | 1
5% | 8 | 1
6% | 8 | 1
7% | 8 | 1
8% | 8 | 1
9% | 8 | 1
10% | 8 | 1
11% | 9 | 1.05 | Very Satisfied
12% | 9 | 1.05
13% | 9 | 1.05
14% | 9 | 1.05
15% | 9 | 1.05
16% | 9 | 1.05
17% | 9 | 1.05
18% | 9 | 1.05
19% | 9 | 1.05
20% | 9 | 1.05
21% | 9 | 1.05
22% | 9 | 1.05
23% | 9 | 1.05
24% | 9 | 1.05
25% | 9 | 1.05
26% | 10 | 1.1 | Extremely Satisfied
27% | 10 | 1.1
28% | 10 | 1.1
29% | 10 | 1.1
30% | 10 | 1.1
31% | 10 | 1.1
32% | 10 | 1.1
33% | 10 | 1.1
34% | 10 | 1.1
35% | 10 | 1.1
36% | 10 | 1.1
37% | 10 | 1.1
38% | 10 | 1.1
39% | 10 | 1.1
40% | 10 | 1.1
41% | 10 | 1.1
42% | 10 | 1.1
43% | 10 | 1.1
44% | 10 | 1.1
45% | 10 | 1.1
46% | 10 | 1.1
47% | 10 | 1.1
48% | 10 | 1.1
49% | 10 | 1.1
50% | 10 | 1.1