## ECI Process Map
Inception
Feasibility
Strategy
Pre-Construction
Construction
Post-Construction
| Feasibility |  | MHA Defined "Stage 0" | ECC 4th Edition Option C Clause X22 - Stage 1 | ECC 4th Edition Option C Clause X22 - Stage 2
| Client Only |  | Client and Contractor
INCEPTION
| Client: |  | Client and Contractor: | Stage 1 Project Team: | Stage 2 Project Team:
Client Brief
Project Mandate (PID)
Establish project objective
Consider project constraints
Identify Key Stakeholders
Identify Project Owner
Identify Project Risk
Project Governance
Agree scope/brief + ECI team
FEASIBILITY
| Client: |  | Client and Contractor: | Stage 1 Project Team: | Stage 2 Project Team:
Establish Budget
Outline Planning Permission
Benefit Realisation Plan
Land / Statutory Considerations
Develop Business Case
Funding applications
Consider options
Desk Studies (archaeology, environment, geotech etc)
Traffic Modelling
Stakeholder management and Communications Plan
STRATEGY
| Client: |  | Client and Contractor: | Stage 1 Project Team: | Stage 2 Project Team:
Procurement strategy
MSF3 Contractor Selection Process (MHA Annex A)
Determine Design responsibility
Develop Design Brief and Commission
Project Execution Plan
Employers Information Requirements
Consider BIM Compliance
Contract Strategy Meeting
Develop EW/Liability and Opportunities Register
Consider CDM and Health and Safety
Review ECI Checklist
X22 Quotation Process
Start Stage One (MHA Annex B)
PRE-CONSTRUCTION
| Client: |  | Client and Contractor: | Stage 1 Project Team: | Stage 2 Project Team:
|  |  | Can be undertaken earlier if required/necessary | Site Investigations
Enabling Works - risk mitigation etc
Complete Design
Engage key suppliers
Detailed Planning Permission
Land Purchase
Secure Funding
Develop BIM Execution Plan
Regular Update of Project Forecast and Programme (refer flowchart 1)
Agree Total of the Prices and Programme (Target Price - MHA Annex C)
Develop/agree ECI Savings (MHA Annex G)
Develop/agree Employment Skills Plan (MHA Annex E)
|  |  |  | Complete Annex D and all Authorisations | Move to Stage 2 - Construction
Version - MSF3 - ECI Process Map - Aug 2019 - 01
Annex A
Annex B
Annex C
Annex D
Client notifies MHA of scheme and Contractor selected
MHA approves start of X22 Stage 1 and appointment of Contractor
MHA provide package order authorisation
Stage 1 deliverables complete and Cost/Programme agreed
Client and Contractor agree to
MOVE TO STAGE 2
Midlands Highways Alliance - Medium Schemes Framework 3
Early Contractor Involvement Process Map
ANNEX B
Variable - to be agreed during Contract Strategy
ANNEX A
Variable - to be agreed
Midlands Highways Alliance - Medium Scheme Framework 3 Annex Milestones

## Notes
MHA MSF3 Early Contractor Involvement Process Map
Notes and Clarifications:
a. | There is no single agreed definition of ECI.
b. | During MSF2, projects benefitted from a typical period of 6 to 12 months of ECI.
c. | MSF2 made no provision for payment to the Contractor during ECI.
d. | MSF3 has provided Clients with the option of using Secondary Option Clause X22 which will introduce a period of paid ECI into the construction contract.
e. | There are alternative routes to work with Contractors at early stages of a project. These include:
(i) ECC 4 Option C, Secondary Option Clause X22/Paid ECI [MSF3],
(ii) ECC 4 Short Form Contract [MSF3],
(iii) Purchase Order [outside of MSF3] etc.
f. | Before entering into contract using MSF3 the Client and Contractor will need to complete the quotation process; STAGE 0.
g. | The Client and Contractor will agree the extent of ECI to be completed under the contract, referred to in X22 as STAGE ONE.
h. | During ECI STAGE ONE the Client and Contractor agree the Total of the Prices (Target Price) for the contract before commencing construction; STAGE TWO.
i. | There are deliverables for each stage of ECC 4th Edition, Option C using Secondary Option Clause X22:
| (i) | To proceed from Stage 0 (ECI Quotation Stage) to Stage One (Early Contractor Involvement)
|  | Ø | Contract Data Part One [provided by Client]
|  | Ø | Contract Data Part Two [provided by Contractor]
|  | Ø | Agreed ECI Scope and Quotation
|  | Ø | Pricing Information [Cl X22.1 (4) "….information which specifies how the Contractor prepares its assessment of the Prices for Stage Two..."] - Demonstrates linkage from MSF3 selection process to Total of the Prices/Project Forecast.
|  | Ø | Project Forecast
|  | Ø | Programme*
|  | Ø | Risk Register/Early Warning Register*
|  | Ø | MSF3 Annex A [Client notifies MHA of Scheme]
|  | Ø | MSF3 Annex B [MHA approves appointment of Contractor and proceed to Stage 1]
|  | * | Best practice, but not ECC Contract Requirement
| (ii) | To proceed from Stage One (Early Contractor Involvement) to Stage Two (Construction Stage)
|  | Ø | Total of the Prices [Target Price]
|  | Ø | Notice to Proceed to Stage Two [provided by NEC Project Manager once approval provided by Client]
|  | Ø | MSF3 Annex C [MHA provides Package Order Authorisation]
|  | Ø | MSF3 Annex D [Stage One deliverables complete. Client and Contractor agree to move to Stage Two; Construction]
|  | * | Best practice, but not ECC Contract Requirement
N.B. Project Forecasts, Programmes and Risk/Early Warning Registers are updated throughout Stage One and Stage Two.
j. | The benefits of ECI may be increased by the introduction of the Contractor to the project team at an earlier stage, in "Very Early ECI".
k. | It may be difficult to enter contract using ECC option C with X22 at the "Very Early" ECI stage, therefore alternative approaches may be considered.
l. | MSF3 FWCB has developed an agenda for a ECI Strategy Meeting for clients to engage with one or more Contractors at a very early stage.
m. | Clients may choose to complete Stage 0 quotation before completing the feasibility and enter contract using MSF3 at a very early stage.
n. | Clients may consider using the Short Contract option within MSF3 to provide for Very Early ECI as a stand alone contract.
o. | Contractors may be prepared to provide Very Early ECI at their risk based on an established business relationship.
p. | Clients could choose to place a Purchase Order for Very Early ECI, outside of the provisions of MSF3.
q. | Early Contractor Involvement has been shown to deliver more successful projects.
r. | MHA offers ECI training to member authorities at all stages of project development, commissioning and delivery.
s. | This training is delivered with the assistance ICE training.
t. | NEC User guides are available to help develop the contract strategy and the preparation on the Contract Documents.
u. | Further support and advice is also available from the Framework Manager.
v. | Effective budget/programme control of the project will require the project scope to be well defined at each stage of the project the FWCB has provided a useful checklist.
w. | Once in STAGE ONE, there is an expectation that the teams will complete the MSF3 Performance Management Toolkit, which includes specific KPIs for ECI.