## Introduction
MHA MSF2 Performance Management Toolkit
Introduction
1.1 | The performance of the project team delivering the project should be rated and monitored by the whole project team in relation to each Work Package carried out under the Framework Agreement. This assessment will be carried out against each of the quality criteria and the accuracy of any Cost Models used in the selection procedure. These performance and accuracy scores will then be used to adjust the current quality scores for the contractor at the end of the scheme.
1.2 | The ten key quality aspects are Product, Service, Right First Time, Cost Management, Time, Safety, Learning and Development, Community, Traffic Management, Innovation and quality for money.
1.3 | In addition to the key quality aspects, there are optional performance elements that measure the performance of the Commissioning Authority and, the tookit also includes the MHA Framework Community KPI's.
1.4 | This spreadsheet contains definitions and guidance on the key performance measures and a toolkit that can be used to collect the required information for each work package both during and at the end of the scheme.
1.5 | For each key quality aspect a number of measures have been defined.
Core measures are expected to be collected for all schemes both during and at the end of the scheme. In scheme core measures are collected at 2 months intervals from the start of work on site.
Optional - locally determined are meaures that teams may wish to adopt locally for Work Packages. The use of these measures needs to be agreed before the start of a scheme. These measures are not used to adjust the quality scores of an individual contractor
Framework - are measures which are collected and reported at a framework level. These measures are not used to adjust the quality scores of an individual contractor
1.6 | The toolkit contains a number of worksheets as described below
Introduction
Scheme Details - Core scheme details including key cost, time and safety data, and current data about scheme including date of scoring
Scheme Scores - A summary of the latest set of scores contained in each of the worksheets and a summary of past scores collected at 2 month intervals.
Scheme Scores - Charts - Charts for each KPI based on the data in the Scheme Scores worksheet
Optional Scheme Scores - A summary of the latest set of optional scores contained in each of the worksheets and a summary of past scores collected at 2 month intervals
Optional Scheme Scores - Charts - Charts for each optional measure based on the data in the Optional Scheme Scores worksheet
MHA MSF2 KPI's - A summary of the KPI's and Optional Measures including definitions, indicator type, frequency of collection. The worksheet is set up with a filter on the top row.
1_Product - Satisfaction with key aspects of product
2_Service - Satisfaction with key aspects of service
3_Right First Time - Looks at the 'whole system' to ensure right first time. Is there a plan, is it communicated, how effectively is it deployed, what level of faliure or non-conformity is arising.
4_Cost Management - Predictability of cost
5_Time - Predictability of time
6_Safety - Key aspects of health and safety
7_Learning and development - Engagement with Employee Skills Plan
8_Community - Impact of projects on the local community
9_Traffic Management - Key aspects of traffic management
10_Innovation and value for money
11_Commissioning Authority Performance - Optional 360 review of Commissioning Authority performance
1.7 | The spreadsheet allows the direct recording of all Core and Optional measures. Whilst suggestions for Optional -Locally Determined measures are included within each of the worksheets 1 to 10 and are carried forward to the Optional Scheme Score Summary they are not used to amend the MHA MSF2 Quality score multiplier. Optional measures should only be used with the agreement of the whole project team but can be a further way of measuring success against the MHA outcomes.
1.8 | The ten worksheets containing the MHA quality criteria are generally formatted in the same way and include a summary MHA score and multiplier, cells to enter core and optional measures, satisfaction criteria (where appropriate) and, key aspects/factors. A typical layout is shown below for 3_Right First Time
How to use the toolkit
2.1 | The toolkit is designed to enable scores to be entered into each of the worksheets for the key criteria (numbered 1 to 11 above) plus, Scheme Details. Enter the required information into the relevant coloured cells within the Scheme Details worksheet and, worksheets 1 to 11.
Information about the Scheme to be entered the first time the toolkit is used. This information should be entered into cells in the Scheme Details worksheet coloured grey with a double border.
In the Scheme Details worksheet, orange cells denote data that will normally be updated each time performance measures are scored including at 2 month intervals during the project and, following completion of the project
In worksheets 1 to 11, green cells denote data that will normally be updated each time performance measures are scored including at 2 month intervals during the project and, following completion of the project
A cell coloured blue with a dashed border in the Scheme Details worksheet is calculated data used for one of the KPI's. Blue cells with a dashed border in a KPI worksheet are linked to the relevant data from the Scheme Details eg 4_Cost Management
Optional measures are entered into cells coloured aqua with a dotted border
The majority of the worksheets are protected against amending or altering content and in the case of satisfaction scores the range of scoring that can be used. Data can generally only be entered into the coloured cells described above.
2.2 | Where appropriate the spreadsheet will automatically convert the scores entered into an MHA score out of 10. For example, the Considerate Constructors score in 8_Community will normally be the overall scheme score issued following the Monitors visit. This will then be converted to an MHA score and the MHA Multiplier used to adjust the quality scores used for Contractor Selection. The relationship between the score and the multiplier is generally shown on each worksheet. Where the conversion data is not shown on the individual worksheet the relevant worksheet containing the data is referenced to ensure that the methodology is transparent to all users
2.3 | The summary information from each of the worksheets 1 to 11 is automatically transferred to the Scheme Scores worksheet and the Optional Scores worksheet.
2.4 | Each time a new set of scores is entered the data in the spreadsheet will be updated. To keep a history of past scores it is recommended that the spreasheet is saved as a new version each time updated scores are entered. To keep a history of the project the previous data in the Scheme Scores worksheet and Optional Scores worksheet should be copied across to a new column (see 2.5 below). It is recommended that each version of the file is saved using the following filename convention. YYYYMMDD_MHA Ref_Scheme Name_Contractor Name_Version No. For example 20150315_051_Lichfield Park_Galliford_V2
2.5 | Before updating the scores, in the worksheet Scheme Scores, select column H and then insert a new empty column. Next select and copy column G (latest scores). Finally using Paste Special - Values, paste the copied data into the inserted blank column. Add the date (MMM-YY) of the previous update into this column in cell H9 . Once this is complete continue to enter the latest set of information into the spreadsheet. Repeat the above process for the Optional Scheme Scores worksheet if Optional Measures are being collected. There will then be a record of previous scores in the toolkit.
Guidance on scores
3.1 | Wherever possible, scores are derived direct from objective data eg Considerate Constructors score, predictabilty of cost and time
3.2 | Where objective scoring is not available, guidance on how to score is provided within each of the relevant worksheets 1 to 11. This can normally be found in the lower half of the worksheet.
3.3 | Coloured cells where scores are entered generally have data validation built in. For example, scores against key aspects based on satisfaction will generally only allow scores against the numbers indicated. This is to encourage positive and collective decisions around scores to aid distinction between different levels of performance.
3.4 | A score of 8 generally indicates that a scheme is performing at the level expected by the MHA. Where a scheme scores higher or lower than 8 it is expected that comments will be provided to outline the reasons for either higher or, lower levels of performance. A comments box is provided for this purpose on each worksheet
In scheme scores
5.1 | In scheme scores are to be collected every 2 months from the start of work on site and submitted to the MHA Framework Manager. The core measure scores are converted to the MHA MSF2 quality multiplier.
5.2 | The MHA MSF2 quality mulitplier during the scheme will be calculated as the average of the scores to date and this will be used to adjust the tender quality score used for selection. The score will be adjusted at the end of the scheme based on the average score during the Work Package.
Guidance on key aspects or factors
6.1 | Where scoring depends on the consideration of 'key aspects or factors' these are listed in the lower half or the spreadheet below the guidance referred to in 3.2 above.
Other worksheets in the toolkit
7.1 | In addition to the worksheets described above, the spreadsheet also contains a number of other worksheets that are used to provide background data to support the calculation of the MHA score eg Considerate Constructors. Where any changes to the scoring mechanism are agreed by the MHA Framework Community Board these will be updated and a new version of the toolkit issued.
Printing
8.1 | Pages are generally formatted to print out on A4 or A3 paper. For worksheets 1 to 11 the pages are generally formatted to print the MHA Score, Scheme Score, Guidance on satisfaction score and, key aspects/factors on individual pages allowing the user to print out as much or, as little as required.
Further information
9.1 | For further information on the MHA Quality Aspects and training and guidance on using the toolkit please contact John Hooper, MHA Framework Manager, Tel : 0116 305 7873 email: john.hooper@leics.gov.uk
9.2 | For any issues that arise with the use of the toolkit please contact David Walters, Staffordshire County Council, Tel : 01785 854024 email: david.walters@staffordshire.gov.uk.
Version | Revisions made since previous version | By
2016-01-01
12 | Optional Scheme Scores and Optional Scheme Scores - Worksheets added to allow capture and record of optional measures | DMW
12 | Comments box added to key quality aspects worksheets to allow capture of comments particularly where performance is different than the norm expected through the framework i.e. eight | DMW
12 | Scheme Details - worksheet amended to clarify information required related to latest target cost and latest predicted outturn cost. Additional cells added to identify names of staff completing the performance toolkit and date of review. Comments box added to worksheet. | DMW
12 | 12_Framework worksheet removed. Measures now collected in Scheme Details worksheet | DMW
2016-07-01
13 | Minor corrections to Scheme Scores worksheet | DMW
13 | Scheme Details worksheet - additional cells added to enable distinction between compensation events that represent change in scope eg additional phase to project and day to day amendments to original project | DMW
13 | Scheme Details worksheet - additional cells added to enable distinction between changes in duration of the project due to change in scope eg addition of an additional phase and day to day amendments to the project | DMW
13 | MHA MSF2 KPI's added Optional KPI 3.3 and 3.4 MHA MFS2 Quality Charter and Commitments | DMW
13 | Optional Scheme Scores and Optional Scheme Scores - Charts added Optional KPI 3.3 and 3.4 | DMW
13 | Right First Time worksheet - addition of optional measures and key aspects to reflect the adoption of the MHA MFS2 Quality Charter and Commitments | DMW

## Scheme Details
Scheme Details
Information on first use |  | Unit/Format | KPI | Notes on information required
Employer |  |  |  | Name of MHA Commissioning Authority (Client)
Employers Representative |  |  |  | Name of Employers Representative (Client)
Project Manager |  |  |  | Name of Project Manager
Supervisor |  |  |  | Name of Supervisor
MHA Ref |  |  |  | MHA Reference for Works Package, 3 digit number
Scheme Name |  |  |  | Name of Works Package
Contractor |  |  |  | Name of Contractor
Contractors Key Person |  |  |  | Name of Key Person
Programme Start Date |  | DD-MMM-YY |  | Agreed start date for the works
Programme End Date |  | DD-MMM-YY |  | Agreed end date for the works
Target Price |  | £ |  | Initial Target Price at MHA Approval to Award
Value of savings identified and used via ECI |  | £ | 10.1 | The value of ECI savings as notified to the MHA at request for Approval to Award following agreement of Target Price
Information at 2 month intervals & end of scheme
Period covered by this submission
Period covered by data in toolkit (from) |  | DD-MMM-YY |  | Period covered by performance data in toolkit, normally the latest 2 month period during scheme or, insert "final scores" at end of scheme
Period covered by data in toolkit (to) |  | DD-MMM-YY
Programme
Actual Start Date |  | DD-MMM-YY |  | Normally the same as the Programme Start Date in cell B10
Latest (and at end of scheme final) estimated Programme End Date |  | DD-MMM-YY |  | Latest (and at end of scheme final) agreed programme end date
Total Agreed Extension |  | days |  | Number of days extension to programme agreed (includes weekends and bank holidays)
Agreed Extension due to change in scope eg an additional phase to the project notified by the Project Manager |  | days |  | Agreed Extension due to change in scope eg an additional phase to the project notified by the Project Manager
Financial
Total Value of agreed Compensation events to date |  | £ |  | The final agreed value of all compensation events notified by the Project Manager and the Contractor
Total Value of agreed Compensation events due to change in scope eg additional phase to project |  | £ |  | The final agreed value of all compensation events notified by the Project Manager that are due to a significant change in scope in the works eg the award of an additional phase to the project
Latest forecast target price (and at the end of the scheme the final adjusted target price) |  | £ |  | Latest in scheme adjusted target price
Latest predicted outturn cost (and at the end of the scheme outturn cost) |  | £ |  | Latest in scheme predicted outturn cost
Safety
Total No. of hours worked on site since construction started |  | No. |  | Used to calculate overall framework measures
Total No. of hours worked on site in period (since last report). |  | No. |  | Used to calculate overall framework measures
Number of RIDDORS in period (since last report) |  | No. |  | Used to calculate overall framework measures
Number of Lost Time Accidents in period (since last report) |  | No. |  | Used to calculate overall framework measures
Total number of exceptions recorded using a Non Conformance Process |  |  |  | See MHA Quality Charter
Number of exceptions recorded in period ie past 2 months |  |  |  | See MHA Quality Charter
Total Number of NCR's closed out in the agreed timescale |  |  |  | See MHA Quality Charter
Calculated Data
Agreed Duration | 0 | days |  | (Programme Start Date to Programme End Date (total calandar days including weekends, bank holidays)
Actual Duration | 0 | days |  | (Programme Actual Start Date to Programme Actual End Date (total calandar days including weekends, bank holidays)
Variation of time - percentage variance of actual to agreed duration | #DIV/0! | % |  | (Actual Duration - Agreed Duration) / Agreed Duration
Predictability of cost (pain/gain share at completion) (in scheme & end of scheme) | #DIV/0! | % | 4.1 | (Latest predicted outturn cost - Latest predicted target cost) / Latest predicted target cost
Pecentage of savings identified and used via ECI | #DIV/0! | % | 10.1 | Value of savings identifed and used via ECI / Initial Target Price at MHA Approval to Award
No of NCR's per £100k | #DIV/0! | No/£100k |  | Total number of exceptions recorded using a Non Conformance Process/(Latest predicted outturn cost (and at the end of the scheme outturn cost)/100000)
Percentage of NCR's closed out in the agreed timescale | #DIV/0! | % |  | Total Number of NCR's closed out in the agreed timescale/Total number of exceptions recorded using a Non Conformance Process
Toolkit Completed By
Completed By (Project Manager)
Completed By (Client)
Completed By (Contractor)
Date of Completion
Comments

## Scheme Scores
Scheme Name | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0
| Scheme Score |  |  | Latest MHA Score | Latest Score
|  |  |  | 0 | 0
1 | Product
1.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | Core |  | 0 | 0
2 | Service
2.1 | Satisfaction against key aspects of service (in scheme & end of scheme) | Core |  | 0 | 0
3 | Right first time
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction (in scheme & end of scheme) | Core |  | 0 | 0
4 | Cost management
4.1 | Predictability of cost (pain/gain share at completion) (in scheme & end of scheme) | Core |  | #DIV/0! | #DIV/0!
5 | Time
5.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | Core |  | 0 | 0
6 | Safety
6.1 | Percentage satisfaction against key aspects of safety (in scheme & end of scheme) | Core |  | 0 | 0
7 | Learning and development
7.1 | Contractors willingness to positively engage in the Employee Skills Plan. ESP in place before start of scheme with a value >£1 million | Core |  | 0 | 0
8 | Community
8.1 | Considerate Constructors Score (in scheme & end of scheme) | Core |  | #N/A | #N/A
9 | Traffic management
9.1 | Satisfaction against key aspects of the service (in scheme & end of scheme) | Core |  | 0 | 0
10 | Innovation and quality for money
10.1 | ECI Savings as a percentage of initial target price | Core |  | #DIV/0! | #DIV/0!
11 | Commissioning Authority Performance
11.1 | Satisfaction against MHA key aspects that provide the right environment to achieve the required outcomes (in scheme & end of scheme) | Optional - Locally determined |  | 0 | 0
| MHA Multiplier |  | Rolling MHA Multiplier for Scheme | Latest MHA Multiplier for Scheme | Latest Score
|  |  |  | From | From
1 | Product
1.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | Core | 0.5 | 0.5 | 0.5
2 | Service
2.1 | Satisfaction against key aspects of service (in scheme & end of scheme) | Core | 0.5 | 0.5 | 0.5
3 | Right first time
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction (in scheme & end of scheme) | Core | 0.5 | 0.5 | 0.5
4 | Cost management
4.1 | Predictability of cost (pain/gain share at completion) (in scheme & end of scheme) | Core | #DIV/0! | #DIV/0! | #DIV/0!
5 | Time
5.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | Core | 0.5 | 0.5 | 0.5
6 | Safety
6.1 | Percentage satisfaction against key aspects of safety (in scheme & end of scheme) | Core | 0.5 | 0.5 | 0.5
7 | Learning and development
7.1 | Contractors willingness to positively engage in the Employee Skills Plan. ESP in place before start of scheme with a value >£1 million | Core | 0.5 | 0.5 | 0.5
8 | Community
8.1 | Considerate Constructors Score (in scheme & end of scheme) | Core | #N/A | #N/A | #N/A
9 | Traffic management
9.1 | Satisfaction against key aspects of the service (in scheme & end of scheme) | Core | 0.5 | 0.5 | 0.5
10 | Innovation and quality for money
10.1 | ECI Savings as a percentage of initial target price | Core | #DIV/0! | #DIV/0! | #DIV/0!
Formulas:
Latest Score = [Latest MHA Score]

## Scheme Scores - Charts
Scheme Name | 0
Contractor | 0
Period | 0
MHA Ref | 0
Commissioning Authority | 0

## Optional Scheme Scores
Scheme Name | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0
| Optional Scheme Score |  |  | Latest MHA Score | Latest Score
|  |  |  | 0 | 2016-01-01
1 | Product
2 | Service
2.2 | Percentage satisfaction of Tier 2 suppliers with MHA Framework Contractor against MHA standard questionnaire | Optional - Locally determined |  | 0 | 0
2.3 | Supply chain payments - percentage of payments to supply chain made in accordancxe with MHA Fair Payment Charter | Optional - Locally determined |  | 0 | 0
3 | Right first time
3.2 | Percentage of disallowed costs due to works not complying with the works information against adjusted target | Optional - Locally determined |  | 0 | 0
3.3 | No of NCR's per £100k | Optional - Locally determined |  | #DIV/0! | #DIV/0!
3.4 | Percentage of NCR's closed out in the agreed timescale | Optional - Locally determined |  | #DIV/0! | #DIV/0!
4 | Cost management
4.2 | Cost Performance - comparison of budget cost of work to actual cost of work performed (percentage) | Optional - Locally determined |  | 0 | 0
4.3 | Accurately priced compensation events - Percentage of initial value of submitted CE's to final agreed value | Optional - Locally determined |  | 0 | 0
4.4 | Accuracy of cost and payment records expressed as a percentage | Optional - Locally determined |  | 0 | 0
4.5 | Percentage of compensation events agreed in relation to the number submitted | Optional - Locally determined |  | 0 | 0
5 | Time
5.2 | Predictability of time | Optional - Locally determined |  | #DIV/0! | #DIV/0!
5.3 | Reliability and accuracy of programming of activities | Optional - Locally determined |  | 0 | 0
5.4 | Accuracy of duration for compensation events | Optional - Locally determined |  | 0 | 0
6 | Safety
7 | Learning and development
7.2 | Percentage of targets achieved against number predicted to be achieved (in scheme & end of scheme) | Optional - Locally determined |  | 0 | 0
8 | Community
8.2 | Overall satisfaction with construction of the works (percentage) | Optional - Locally determined |  | 0 | 0
8.3 | Percentage of customer enquiries responded to first time against target | Optional - Locally determined |  | 0 | 0
8.4 | Contractors level of engagement with the Scheme communications plan | Optional - Locally determined |  | 0 | 0
8.5 | Percentage of targets in communication plan met against number predicted to be achieved | Optional - Locally determined |  | 0 | 0
9 | Traffic management
10 | Innovation and quality for money
10.2 | Satisfaction against key aspects that provide the right environment for innovation and value for money | Optional - Locally determined |  | 0 | 0

## Optional Scheme Scores - Charts
Scheme Name | 0
Contractor | 0
Period covered by data in toolkit | From | 0 | To | 0
MHA Ref | 0
Commissioning Authority | 0

## MHA MSF2 KPI's
| Category | Purpose | Factors/Key Aspects |  | Measure | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2 | Comments | Source of data
1 | Product | To determine the overall level of Employer satisfaction with the completed product. | Construction of main works; handover, acceptance, inspections and as-built records; post-project review; risk & opportunities register; sustainable construction, minimising waste creation and maximising recycling and opportunities plan. | 1.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes |  | In scheme progress and end of scheme review meeting
2 | Service | To determine the overall level of Employer satisfaction with the service of the supplier during the project. | Organisation and management; procurement of specialists and suppliers; supply chain; management and improvement of Employer relationships; management and improvement of customer and third party relationships; innovation and value for money; management of change; collaborative working. | 2.1 | Satisfaction against key aspects of service (in scheme & end of scheme) | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes |  | In scheme progress and end of scheme review meeting
2 | Service |  |  | 2.2 | Percentage satisfaction of Tier 2 suppliers with MHA Framework Contractor against MHA standard questionnaire | Optional - Locally determined | Post scheme satisfaction survey carried out by MHA Framework Contractor maximum 4 weeks after completion of scheme. Survey to be developed from framework contractor's existing processes. | Scheme | End of scheme
2 | Service |  |  | 2.3 | Supply chain payments - percentage of payments to supply chain made in accordancxe with MHA Fair Payment Charter | Optional - Locally determined | Percentage of payments to supply chain made in accordance with MHA Fair Payment Charter | Scheme | In Project - 2 month intervals |  |  | To ensure prompt payments to Tier 2 and 3 supply chain | Expressed as a percentage of total supply chain payments
3 | Right first time | To assess the impact on the Employer of any defects and reworking. | Avoiding defective works; quality management system. | 3.1 | Satisfaction with key aspects that reduce the risk of defects in construction (in scheme & end of scheme) | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes |  | In scheme progress and end of scheme review meeting
3 | Right first time |  |  | 3.2 | Percentage of disallowed costs due to works not complying with the works information against adjusted target | Optional - Locally determined |  | Scheme | In Project - 2 month intervals
|  |  |  | 3.3 | No of NCR's per £100k | Optional - Locally determined |  | Scheme | In Project - 2 month intervals |  |  |  | From QMS and scheme details
|  |  |  | 3.4 | Percentage of NCR's closed out in the agreed timescale | Optional - Locally determined |  | Scheme | In Project - 2 month intervals |  |  |  | From QMS
4 | Cost management | To measure the accuracy of cost predication and reliability of cost control. | Ensuring accurate estimating and forecasting, predictability of cost, and accuracy of cost and payment records. | 4.1 | Predictability of cost (pain/gain share at completion) (in scheme & end of scheme) | Core | Percentage variation of cost against adjusted target price (% pain/gain share) | Scheme | In Project - 2 month intervals & Within 3 months of end of scheme | Yes | Yes |  | Contract data as adjusted
4 | Cost management |  |  | 4.2 | Cost Performance - comparison of budget cost of work to actual cost of work performed (percentage) | Optional - Locally determined | Comparison of budgeted cost of work to actual cost of work performed | Scheme | In Project - 2 month intervals
4 | Cost management |  |  | 4.3 | Accurately priced compensation events - Percentage of initial value of submitted CE's to final agreed value | Optional - Locally determined | Ratio of cumulative initially submitted value of CE's to the final agreed value of those same events. | Scheme | In Project - 2 month intervals |  |  | Based on Compensation Event initial values submitted by the Contractor and the final value reviewed and agreed with the Commissioning Authority | From EWN/CE register
4 | Cost management |  |  | 4.4 | Accuracy of cost and payment records expressed as a percentage | Optional - Locally determined | From audits of submitted cost information | Scheme | In Project - 2 month intervals
4 | Cost management |  |  | 4.5 | Percentage of compensation events agreed in relation to the number submitted | Optional - Locally determined | From EWN/CE register | Scheme | In Project - 2 month intervals |  |  |  | From EWN/CE register
5 | Time | To measure the reliability of time estimates for both design and construction. | Reliability of programming; predictability of time. | 5.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes |  | In scheme progress and end of scheme review meeting
5 | Time |  |  | 5.2 | Predictability of time | Optional - Locally determined | Percentage variation of forecast duration against target programme | Scheme | In Project - 2 month intervals and End of Scheme | Yes | Yes |  | Client data
5 | Time |  |  | 5.3 | Reliability and accuracy of programming of activities | Optional - Locally determined | Programmed activities complete as a percentage of activities due to be complete | Scheme | In Project - 2 month intervals
5 | Time |  |  | 5.4 | Accuracy of duration for compensation events | Optional - Locally determined | Ratio of agreed cumulative requests (as a percentage) for additional time compared to the submitted periods of those CE's | Scheme | In Project - 2 month intervals and End of Scheme
6 | Safety | To measure health and safety aspects on the project. | Health, welfare and development of the workforce; compliance with safety legislation and regulations; safety of the public. | 6.1 | Percentage satisfaction against key aspects of safety (in scheme & end of scheme) | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes |  | In scheme progress and end of scheme review meeting
7 | Learning and development | To measure the success of skills development against the Employment and Skills Plan (ESP). | New entrant’s skills development, existing workforce skills development, progression into employment | 7.1 | Contractors willingness to positively engage in the Employee Skills Plan. ESP in place before start of scheme with a value >£1 million | Core | ESP in place before start of scheme with a value >£1 million | Scheme | At start of construction work | Yes | Yes (>£1m) |  | MHA
7 | Learning and development |  |  | 7.2 | Percentage of targets achieved against number predicted to be achieved (in scheme & end of scheme) | Optional - Locally determined | Achievement of targets set in plan | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes (>£1m)
8 | Community | To measure how the impact of projects on the local community is minimised before, during and after completion. | Customer Care, working with the local community, Considerate Constructor. | 8.1 | Considerate Constructors Score (in scheme & end of scheme) | Core | Considerate Constructors Scheme Inspection | Scheme | Latest score from CCS Monitor visit | Yes | Yes | The scheme score is based on the most recent CCS report | CCS Score
8 | Community |  |  | 8.2 | Overall satisfaction with construction of the works (percentage) | Optional - Locally determined | Frontager scheme satisfaction survey | Scheme | End of scheme
8 | Community |  |  | 8.3 | Percentage of customer enquiries responded to first time against target | Optional - Locally determined | Register of enquiries | Scheme | In Project - 2 month intervals
8 | Community |  |  | 8.4 | Contractors level of engagement with the Scheme communications plan | Optional - Locally determined | Project Manager score (0 Totally dissatisfied, 2 Very dissatisfied , 5 Slightly dissatisfied, 6 Neither satisfied nor dissatisfied, 8 satisfied, 9 very satisfied, 10 exceptionally satisfied) | Scheme | Within 3 months of the start of the scheme
8 | Community |  |  | 8.5 | Percentage of targets in communication plan met against number predicted to be achieved | Optional - Locally determined | Achievement of targets set in communication plan | Scheme | In Project - 2 month intervals
9 | Traffic management | To measure the success of minimising the impact of projects on highway users through appropriate traffic management. | Disruption and congestion, all highway users’ considered, appropriate and up to date information for highway users, safety of measures. | 9.1 | Satisfaction against key aspects of the service (in scheme & end of scheme) | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
10 | Innovation and quality for money | To measure the success of innovation through cashable and non-cashable efficiency savings and, demonstrate ongoing value for money. | Continuous improvement through Contractor and supply chain, early Contractor and Supplier involvement, opportunities plan, innovation and value for money. | 10.1 | ECI Savings as a percentage of initial target price | Core | ECI Savings Register in place and supplied to MHA as part of approval to award package order | Scheme | At request to MHA for approval to award package order | Yes | Yes | ECI Savings register in place and provided to MHA at time request for approval to place a package order (ie after agreement of target cost) | MHA
10 | Innovation and quality for money |  |  | 10.2 | Satisfaction against key aspects that provide the right environment for innovation and value for money | Optional - Locally determined | Satisfaction against key aspects Project Manager score (0 Totally dissatisfied, 2 Very dissatisfied , 5 Slightly dissatisfied, 6 Neither satisfied nor dissatisfied, 8 satisfied, 9 very satisfied, 10 exceptionally satisfied) | Scheme | Within 4 weeks of the end of scheme |  |  | Post package order approval scheme savings register in place and provided to MHA within 4 weeks of end of scheme | MHA
11 | Commisioning Authority Performance | To measure the approach of the Commissioning Authority in respect of the outcomes established by the MHA |  | 11.1 | Satisfaction against MHA key aspects that provide the right environment to achieve the required outcomes (in scheme & end of scheme) | Optional - Locally determined | Satsifaction against key aspects Contractor score | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
12 | MHA Framework Community Performance |  |  | 12.1a | Total No. of hours worked on site since construction started | Core | Turnover measure for contractors | Framework | Collected and reported for each Framework Community Board Meeting | Yes | Yes
|  |  |  | 12.1b | Total No. of hours worked on site in period (since last report). | Core | Turnover measure for contractors | Framework | Collected and reported for each Framework Community Board Meeting | Yes | Yes
|  |  |  | 12.2a | Number of RIDDORS in period (since last report) | Core |  | Framework | Collected and reported for each Framework Community Board Meeting | Yes | Yes
|  |  |  | 12.2b | Number of Lost Time Accidents in period (since last report) | Core |  | Framework | Collected and reported for each Framework Community Board Meeting | Yes | Yes

## 1_Product
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
1.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | 0 | 0 | 0.5 | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores | Measure | Score
1.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | 0 |  |  | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Question 1.1a and 1.1b | Guidance on scores
MHA Multiplier
0 | Totally dissatisfied | More than one key aspect is currently unacceptable to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.6
5 | Slightly dissatisfied | Some minor elements of the key aspects are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the overall service. Use only in exceptional circumstances with the approval of the MHA Framework Manager | [5 empty] | 0.9
8 | Satisfied | All key aspects are satisfactory. The majority of issues that contribute to the delivery of a quality product are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate action taken | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering a quality product are satisfactory. All issues that contribute to the delivery of a quality product are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering a quality product considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. | [5 empty] | 1.1
Key Aspects (examples)
| Construction of main works | Compliance with scheme design
| Handover | Outstanding works at handover
Acceptance inspections and as-built records
| Post project review | Review carried out in a timely manner including performance management information
Risk register
Sustainable construction
Minimise waste creation and maximise recycling
Opportunties plan
| Work Package Commitments/Promises | Compliance with quality statements relevant to work package made in original framework submission

## 2_Service
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
2.1 | Satisfaction against key aspects of service (in scheme & end of scheme) | 0 | 0 | 0.5 | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores | Measure | Score
2.1 | Satisfaction against key aspects of service (in scheme & end of scheme) |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
2.2 | Percentage satisfaction of Tier 2 suppliers with MHA Framework Contractor against MHA standard questionnaire |  |  |  | Optional - Locally determined | Post scheme satisfaction survey carried out by MHA Framework Contractor maximum 4 weeks after completion of scheme. Survey to be developed from framework contractor's existing processes. | Scheme | End of scheme
2.3 | Supply chain payments - percentage of payments to supply chain made in accordancxe with MHA Fair Payment Charter |  |  |  | Optional - Locally determined | Percentage of payments to supply chain made in accordance with MHA Fair Payment Charter | Scheme | In Project - 2 month intervals
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Question 2.1a and 2.1b | Guidance on scores
Multipler
0 | Totally dissatisfied | More than one key aspect is currently unacceptable to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.6
5 | Slightly dissatisfied | Some minor elements of the key aspects are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the overall service. Use only in exceptional circumstances with the approval of the MHA Framework Manager | [5 empty] | 0.9
8 | Satisfied | All key aspects of delivering a quality service are satisfactory. The majority of issues that contribute to the provision of a quality service are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate action taken | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering a quality service are satisfactory. All issues that contribute to the delivery of a quality service are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering a quality service considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. | [5 empty] | 1.1
Key Aspects (examples)
| Organisation & management | At ECI, review pre-construction information and liaise with Designer to ‘design out’ non conformities
Works Quality Plan in place pro-actively in advance of work starting to allow review
Appropriate documentation submitted pro-actively and followed e.g. test certificates etc
Quality statements in place sufficiently in advance of activities
Site inductions, task specific training, toolbox talks, briefings include quality
Ensure all people on-site receive and understand project specific quality induction
Pre-start staff competency checks with plant and equipment inspected against quality plan
Regular reviews and checks against framework and site quality KPI’s
| Procurement of specialists and suppliers | At ECI identify all 3rd parties and includes discussion on quality
Selection process enables selection of quality subcontractors and suppliers
Supply chain inductions include quality plan
Localism including local small and medium enterprises (SME) involvement and employment
| Management and improvement of Employer relationships | Briefings and feedback include quality, regular quality meetings, quality feedback
Management and improvement of customer and third party relationships
Innovation and value for money
Management of change
Colloborative working

## 3_Right First Time
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction (in scheme & end of scheme) | 0 | 0 | 0.5 | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores | Measure | Score
3.1 | Satisfaction with key aspects that reduce the risk of defects in construction (in scheme & end of scheme) |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
3.2 | Percentage of disallowed costs due to works not complying with the works information against adjusted target |  |  |  | Optional - Locally determined |  | Scheme | In Project - 2 month intervals
3.3 | No of NCR's per £100k | #DIV/0! |  |  | Optional - Locally determined |  | Scheme | In Project - 2 month intervals
3.4 | Percentage of NCR's closed out in the agreed timescale | #DIV/0! |  |  | Optional - Locally determined |  | Scheme | In Project - 2 month intervals
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Question 3.1a and 3.1b | Guidance on scores | [5 empty] | MHA Multiplier
0 | Totally dissatisfied | More than one key aspect is currently unacceptable to the extent that it calls into question the suppliers capability to deliver a product right first time. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect is unsatisfactory to the extent that the Project Manager considers that significant intervention is required eg a serious failure of the quality management system resulting in significant additional cost as a result of failure to comply with the Works Information. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
5 | Slightly dissatisfied | Some minor elements of the key aspects are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the 'right first time' performance. Use only in exceptional circumstances with the approval of the Framework Manager | [5 empty] | 0.9
8 | Satisfied | All key aspects of delivering a product right first time are satisfactory. The majority of quality issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. Agreed tender promises are being delivered. | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering a product right first time are satisfactory. All quality issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause if any issues is promptly investigated and appropriate steps taken. Agreed tender promises are being delivered. There is a high level of confidence that only a minimal number of minor defects will be outstanding at scheme handover. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering a product right first time considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. No defects are outstanding at scheme handover. | [5 empty] | 1.1
Key Aspects
| Mitigating risks through planning | At ECI, review pre-construction information and liaise with Designer to ‘design out’ non conformities
Works Quality Plan in place pro-actively in advance of work starting to allow review
Appropriate documentation submitted pro-actively and followed e.g. test certificates etc
Quality statements in place sufficiently in advance of activities
| Competent people | Site inductions, task specific training, toolbox talks, briefings include quality
Ensure all people on-site receive and understand project specific quality induction
Pre-start staff competency checks with plant and equipment inspected against quality plan
| Workforce consultation | Briefings and feedback include quality, regular quality meetings, quality feedback
| Continually improving | Process for investigating the cause of defects in place and followed
Process for mitigating impact and ensuring that defects are avoided in the future in place and followed
Quality Audits
| Supply Chain H & S Management | At ECI identify all 3rd parties and includes discussion on quality
Selection process enables selection of quality subcontractors and suppliers
Supply chain inductions include quality plan
| Monitoring performance | Regular reviews and checks against framework and site quality KPI’s
Quality Management System
| MSF2 Quality Charter and Commitments | Proposals are aligned with the requirements of the customers design and specification
Every package of work has an agreed Inspection and Test plan (ITP) and effective checking and verification regime in place
The acceptance criteria for the ITP's meet all the relevant specification, contract and employer's requirements
Ensure all exceptions are recorded using a Non Conformance (NCR) process and they contain agreed corrective and preventative actions
NCR's are closed out in an agreed timetable to avoid compromising follow on work which would otherwise be compliant
Measure, record, review and learn from all NCR's and defects throughout the contract, providing customer assurance that quality standards are being achieved
Ensure ambiguities or omissions are highlighted early to avoid uncessary errors and waste
Maintain essential and sufficient documentation to demonstrate that the product has been installed in a compliant manner
Record and report our quality performance through the Framework Community Board (FCB)
Use MSF2 as a conduit for learning and innovation to improve quality and service performance to customers demonstrating the benefits of the collaborative framework

## 4_Cost management
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
4.1 | Predictability of cost (pain/gain share at completion) (in scheme & end of scheme) | #DIV/0! | #DIV/0! | #DIV/0! | Core | Percentage variation of cost against adjusted target price (% pain/gain share) | Scheme | In Project - 2 month intervals & Within 3 months of end of scheme | Yes | Yes
Scores | Measure | Score
4.1 | Predictability of cost (pain/gain share at completion) (in scheme & end of scheme) | #DIV/0! | #DIV/0! | #DIV/0! | Core | Percentage variation of cost against adjusted target price (% pain/gain share) | Scheme | In Project - 2 month intervals & Within 3 months of end of scheme | Yes | Yes
Data for the above is derived from the Scheme Details worksheet. Please ensure either end of scheme or inscheme data is entered
4.2 | Cost Performance - comparison of budget cost of work to actual cost of work performed (percentage) |  |  |  | Optional - Locally determined | Comparison of budgeted cost of work to actual cost of work performed | Scheme | In Project - 2 month intervals
4.3 | Accurately priced compensation events - Percentage of initial value of submitted CE's to final agreed value |  |  |  | Optional - Locally determined | Ratio of cumulative initially submitted value of CE's to the final agreed value of those same events. | Scheme | In Project - 2 month intervals
4.4 | Accuracy of cost and payment records expressed as a percentage |  |  |  | Optional - Locally determined | From audits of submitted cost information | Scheme | In Project - 2 month intervals
4.5 | Percentage of compensation events agreed in relation to the number submitted |  |  |  | Optional - Locally determined | From EWN/CE register | Scheme | In Project - 2 month intervals
#DIV/0!
Comments
| Question 4.1 | MHA Multiplier
For Multiplier see 4_Cost Management Multiplier worksheet

## 5_Time
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
5.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | 0 | 0 | 0.5 | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
|  |  |  | #DIV/0! |  | Percentage variance from Scheme Details
Scores | Measure | Score
Percentage Variance
5.1 | Percentage satisfaction against key aspects of product (in scheme & end of scheme) | 0 |  |  | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into the above 'orange' cell is limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below.
The percentage predictability of time is derived from the Scheme Details worksheet
5.2 | Predictability of time | #DIV/0! |  |  | Optional - Locally determined | Percentage variation of forecast duration against target programme | Scheme | In Project - 2 month intervals and End of Scheme
5.3 | Reliability and accuracy of programming of activities |  |  |  | Optional - Locally determined | Programmed activities complete as a percentage of activities due to be complete | Scheme | In Project - 2 month intervals
5.4 | Accuracy of duration for compensation events |  |  |  | Optional - Locally determined | Ratio of agreed cumulative requests (as a percentage) for additional time compared to the submitted periods of those CE's | Scheme | In Project - 2 month intervals and End of Scheme
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Question 5.1 | Guidance on scores | [5 empty] | MHA Multiplier
0 | Totally dissatisfied | More than one key aspect is currently unacceptable to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter will have been discussed at Framework Community Board | [5 empty] | 0.6
5 | Slightly dissatisfied | Some minor elements of the key aspects are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the overall service. Use only in exceptional circumstances with the approval of the MHA Framework Manager | [5 empty] | 0.9
8 | Satisfied | All key aspects of delivering the project on time are satisfactory. The majority of issues that contribute to the provision of delivering the project on time are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate action taken | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering the project on time are satisfactory. All issues that contribute to the delivery of the project on time are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering the project on time considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. | [5 empty] | 1.1
Key Aspects
| Predict & Forecast | Was it provided with target price
Does it show resources, constraints
| Monitor & Control | Regular update to programme
Advise on activities, outputs, durations, resources, engineering and traffic management logic and constraints
Mitigate increase in time
Accuracy/time prediction
| Reporting | Input as built information into Accepted Programme
Produce first and following Programmes for Acceptance
Periodic review and analysis of progress
Adjust and implement future activity outputs and durations
Investigate, identify and implement improvements

## 6_Safety
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
6.1 | Percentage satisfaction against key aspects of safety (in scheme & end of scheme) | 0 | 0 | 0.5 | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores | Measure | Score
6.1 | Percentage satisfaction against key aspects of safety (in scheme & end of scheme) |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Question 6.1a and 6.1b | Guidance on scores | [5 empty] | Multiplier
0 | Totally dissatisfied | More than one key aspect is unsatisfactory to the extent that it calls into question the suppliers capability. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect is unsatisfactory to the extent that the Project Manager considers that significant intervention is required. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
5 | Slightly dissatisfied | Some minor elements of the key aspects are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the health and safety performance. Use only in exceptional circumstances with the approval of the MHA Framework Manager | [5 empty] | 0.9
8 | Satisfied | All key aspects of health and safety are satisfactory. The agreed commitments and promises made at framework tender stage and individual work package are being met. | [5 empty] | 1
9 | Very satisfied | All key aspects of health and safety are satisfactory and there is evidence that some Health and Safety aspects are exceeding agreed expectations. The supplier is proactive in identifying best practice and can evidence that additional activities are being undertaken which provide a benefit over and above the agreed tender promises at no additional direct cost to the Client. The suppllier can evidence that the best practice has been taken up by other suppliers within the MHA Framework. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of health and safety considerably exceed expectations with active monitoring of their own and, the supply chain arrangements. The scheme may have received an award from a recognised body for health and safety management. The supplier can evidence work undertaken without an increase to the cost of the work package and, which has been deployed on other schemes, suppliers within and outside the MHA Framework. | [5 empty] | 1.1
Key Aspects
| Mitigating risks through planning | At ECI, review pre-construction information and liaise with CDM coordinator/designer to ‘design out’ high risk activities
H&S Plan in place pro-actively in advance of work starting to allow review
Appropriate documentation eg method statements submitted pro-actively and followed e.g. risk assessment, method statements
| Workforce | Pre-employment assessment, site inductions, task specific training, toolbox talks, method statement briefings
Briefings and feedback, regular safety committee meetings, welfare surveys, training feedback
Welfare facilities compliant with CDM 2007
| Continually improving | Reviews near misses/accidents/incidents with HSEQ Manager
| Supply Chain H & S Management | At ECI identify all 3rd parties and set-up communication channels
Pre-start safety meetings, toolbox talks, regular safety meetings, sub contractoor operatives fully briefed on Method Statements and Risk Assessments
| Monitoring performance | Regular reviews and project health checks against framework and site KPI’s
| Effectiveness of safety system | Near misses

## 7_Learning & Development
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
7.1 | Contractors willingness to positively engage in the Employee Skills Plan. ESP in place before start of scheme with a value >£1 million | 0 | 0 | 0.5 | Core | ESP in place before start of scheme with a value >£1 million | Scheme | At start of construction work | Yes | Yes >1m
Scores | Measure | Score
7.1 | Contractors willingness to positively engage in the Employee Skills Plan (ESP) |  |  |  | Core | ESP in place before start of scheme with a value >£1 million | Scheme | At start of construction work | Yes | Yes >1m
ESP not required for scheme value less than £1,000,000
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
7.2 | Percentage of targets achieved against number predicted to be achieved (in scheme & end of scheme) |  |  |  | Optional - Locally determined | Achievement of targets set in plan | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes (>£1m)
To help understand performance different than that expected through the Framework, please provide comments below where the Contractor did not positively engage in the completion of an ESP before the start of a scheme with a value of >£1million
Comments

## 8_Community
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score (0-10) | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
8.1 | Considerate Constructors Score (in scheme & end of scheme) | 0 | #N/A | #N/A | Core | Considerate Constructors Scheme Inspection | Scheme | Latest score from CCS Monitor visit | Yes | Yes
Scores | Measure | Score
8.1 | Considerate Constructors Score (in scheme & end of scheme) |  |  |  | Core | Considerate Constructors Scheme Inspection | Scheme | Latest score from CCS Monitor visit | Yes | Yes
Insert the Considerate Constructor score for the site (out of 50)
8.2 | Overall satisfaction with construction of the works (percentage) |  |  |  | Optional - Locally determined | Frontager scheme satisfaction survey | Scheme | End of scheme
8.3 | Percentage of customer enquiries responded to first time against target |  |  |  | Optional - Locally determined | Register of enquiries | Scheme | In Project - 2 month intervals
8.4 | Contractors level of engagement with the Scheme communications plan |  |  |  | Optional - Locally determined | Project Manager score (0 Totally dissatisfied, 2 Very dissatisfied , 5 Slightly dissatisfied, 6 Neither satisfied nor dissatisfied, 8 satisfied, 9 very satisfied, 10 exceptionally satisfied) | Scheme | Within 3 months of the start of the scheme
8.5 | Percentage of targets in communication plan met against number predicted to be achieved |  |  |  | Optional - Locally determined | Achievement of targets set in communication plan | Scheme | In Project - 2 month intervals
#N/A
Comments
| Question 8.1 | MHA Multiplier
See Worksheet 8_Community Score Calculation

## 9_Traffic Management
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
9.1 | Satisfaction against key aspects of the service (in scheme & end of scheme) | 0 | 0 | 0.5 | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores | Measure | Score
9.1 | Satisfaction against key aspects of the service (in scheme & end of scheme) |  |  |  | Core | Satisfaction against key aspects | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Questions 9.1a and 9.1b | Guidance for scoring | [5 empty] | MHA Multiplier
0 | Totally dissatisfied | More than one key aspect is currently unacceptable to the extent that it calls into question the suppliers capability to deliver traffic management. The Project Manager will have written to the suppliers Director and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.5
2 | Very dissatisfied | A key aspect is unsatisfactory to the extent that the Project Manager considers that significant intervention is required eg a serious failure of the traffic management system resulting in significant actual or reputational issues such as failure to comply with Chapter 8 of the Traffic Signs Manual. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager and the matter raised at Framework Community Board. | [5 empty] | 0.6
5 | Slightly dissatisfied | Some minor aspects are currently unacceptable and slightly outweigh those which are satisfactory to the extent that the Project Manager seeks improvement. The concerns should have been raised at progress meeting minutes/action points | [5 empty] | 0.8
6 | Neither satisfied or dissatisfied | The Project Manager is neither satisfied or dissatisfied with the traffic management systems. Use only in exceptional circumstances with the approval of the Framework Manager | [5 empty] | 0.9
8 | Satisfied | All key aspects of the traffic management system are satisfactory. The majority of issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause of any issues is promptly investigated and appropriate steps taken. Agreed tender promises are being delivered. | [5 empty] | 1
9 | Very satisfied | All key aspects of delivering traffic management right first time are satisfactory. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager. The cause if any issues is promptly investigated and appropriate steps taken. Agreed tender promises are being delivered. There is a minimal number of issues in relation to traffic management being reported by highway users. | [5 empty] | 1.05
10 | Exceptionally satisfied | All key aspects of delivering traffic management considerably exceed expectations. All issues are being identified by the suppliers own systems and promptly reported to the Project Manager with none remaining open longer than the agreed rectification period. The number of compliements received for traffic management exceeds the number of complaints. | [5 empty] | 1.1
Key Aspects
Disruption and congestion minimised
All highway users considered
Appropriate and up to date information through a variety of media
Safety of measures
Maintenance of signing including diversion routes
Removal of temporary signing when no longer required

## 10_Innovation & Value for Money
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
10.1 | ECI Savings as a percentage of initial target price | #DIV/0! | #DIV/0! | #DIV/0! | Core | ECI Savings Register in place and supplied to MHA as part of approval to award package order | Scheme | At request to MHA for approval to award package order | Yes | Yes
Scores | Measure | Score
10.1 | ECI Savings as a percentage of initial target price | #DIV/0! |  |  | Core | ECI Savings Register in place and supplied to MHA as part of approval to award package order | Scheme | At request to MHA for approval to award package order | Yes | Yes
10.2 | Satisfaction against key aspects that provide the right environment for innovation and value for money |  |  |  | Optional - Locally determined | Satisfaction against key aspects Project Manager score (0 Totally dissatisfied, 2 Very dissatisfied , 5 Slightly dissatisfied, 6 Neither satisfied nor dissatisfied, 8 satisfied, 9 very satisfied, 10 exceptionally satisfied) | Scheme | Within 4 weeks of the end of scheme
Scores to be entered into the above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
#DIV/0!
Comments
Score | Question 10.2 | Guidance on scoring
0 | Totally dissatisfied | No commitment to innovate. The Project Manager will have written to the suppliers Director and the MHA Manager.
2 | Very dissatisfied | The supplier has developed a savings/innovations/opportunities register but few opportunities have been identifed and delivered. The Project Manager will have written to the suppliers Framework Manager and the MHA Framework Manager.
5 | Slightly dissatisfied | Some minor aspects of the development of the savings/innovations/opportunties register are unacceptable and outweigh those which are satisfactory
6 | Neither satisfied or dissatisfied | The savings/innovations/opportunities register been developed but, the Project Manager is neither satisfied or dissatisfied with the willingness to innovate and demonstrate value for money
8 | Satisfied | The Contractor demonstrates an adequate commitment to developing the savings/innovations/opportunities register in line with the commitments made at Framework Tender Stage and, individual work package requirements.
9 | Very satisfied | The Contractor demonstrates an good commitment to developing the savings/innovations/opportunities register and successfully implements most of the aspects identified and shares the success with the Framework Community
10 | Exceptionally satisfied | The Contractor demonstrates an excellent commitment to developing the savings/innovations/opportunities register implements the aspects identified and captures and shares the success with the Framework Community.
Key Aspects
Early and ongoing Contractor and Supplier involvement
Opportunities plan
Pull value and innovation up through supply chain
Culture

## 11_Commissioning Authority
Scheme Name | 0 | MHA Ref | 0
Contractor | 0 | Commissioning Authority | 0
Period | 0 | To | 0
Summary | Measure | Score | MHA Score | MHA Multiplier | Type | Method | Applies to | Frequency | Lot 1 (>£5m) | Lot 2
11.1 | Satisfaction against MHA key aspects that provide the right environment to achieve the required outcomes (in scheme & end of scheme) |  | 0 | N/A | Optional - Locally determined | Satsifaction against key aspects Contractor score | Scheme | In Project - 2 month intervals & Within 4 weeks of the end of scheme | Yes | Yes
Scores to be entered into 11.1 above are limited to the following values 0, 2, 5, 6, 8, 9, 10 as defined below
To help understand performance different than that expected through the Framework, please provide comments below for a score other than eight
Comments
Score | Question 11.1
0 | Totally dissatisfied | No commitment to achieve the outcomes of the MHA. The Contractors Framework Manager will have written to the Commissioning Authority and the MHA Manager.
2 | Very dissatisfied | The Commissioning Authority has managed the Works Package but with limited reference to the outcomes of the MHA. The Contractors Framework Manager will have written to the Commissioning Authority and the MHA Manager. Client not engaged with Performance Toolkit, Toolkit not in use.
5 | Slightly dissatisfied | Some aspects of Commissioning Authority approach towards achieving the outcomes of the MHA have been implemented but are generally outweighed by those which are absent. Client not engaged with Performance Toolkit which is not regulary used.
6 | Neither satisfied or dissatisfied | The Contractor is neither satisfied or dissatisfied with the willingness to achieve the outcomes of the MHA. This options should only be chosen following consultation with the MHA Framework Manager. Client not fully engaged with use of Performance Toolkit.
8 | Satisfied | The Commissioning Authority demonstrates a commitment to achieveing the outcomes of the MHA in line with the Framework Information and individual work package requirements. Client fully engaged in use of Performance Toolkit and regularly submitted.
9 | Very satisfied | The Commissioning Authority demonstrates an good commitment to achieveing the outcomes of the MHA and shares the success with the Framework Community. Client fully engaged with use of Performance Toolkit, jointly agreed, regularly submitted, optional measures in use, good practice being captured and shared in case studies.
10 | Exceptionally satisfied | The Commissioning Authority demonstrates an excellent commitment to achieving the outcomes of the MHA in all aspects and captures and shares the success with the Framework Community. Client fully engaged with use of Performance Toolkit which is regularly submitted, good practice being captured and shared in case studies with development of optional measures.
Key Aspects
Clarity of instructions received
Quality/clarity of feedback
Clarity of client's roles and responsibilities
Flexibility and responsiveness
Liaison
Communications of change
Friendly but business-like;
Proactive rather than reactive;
Flexible, where all parties are prepared to change;
Respectful of differences;
risk is appropriately proportioned
Act in a spirit of openness and trust;
Act to secure best value for money and continuous improvement;
Objectives are shared with long-term commitment from all parties by establishing an effective joint management and decision-making structure;
Enables innovation and implements change in a timely manner
So far as possible, avoid conflicts or disagreements and, should they arise, will resolve them promptly together.
Use of Performance Management Toolkit

## 8_Community Score Calculation
CCS Score | MHA Score | MHA Multiplier
1 | 0 | 0.5 | Totally dissatisfied
2 | 0 | 0.5
3 | 0 | 0.5
4 | 0 | 0.5
5 | 0 | 0.5
6 | 0 | 0.5
7 | 0 | 0.5
8 | 0 | 0.5
9 | 0 | 0.5
10 | 0 | 0.5
11 | 0 | 0.5
12 | 0 | 0.5
13 | 0 | 0.5
14 | 0 | 0.5
15 | 0 | 0.5
16 | 0 | 0.5
17 | 0 | 0.5
18 | 0 | 0.5
19 | 0 | 0.5
20 | 0 | 0.5
21 | 0 | 0.5
22 | 0 | 0.5
23 | 0 | 0.5
24 | 0 | 0.5
25 | 0 | 0.5
26 | 0 | 0.5
27 | 0 | 0.5
28 | 2 | 0.6 | Very dissatisfied
29 | 2 | 0.6
30 | 2 | 0.6
31 | 2 | 0.6
32 | 5 | 0.8 | Slighty dissatisfied
33 | 5 | 0.8
34 | 6 | 0.9 | Neither
35 | 8 | 1 | Satisfied | CCS Average Score
36 | 8 | 1
37 | 8 | 1
38 | 8 | 1
39 | 8 | 1
40 | 8 | 1
41 | 8 | 1
42 | 8 | 1
43 | 9 | 1.05 | Very satisfied
44 | 9 | 1.05
45 | 10 | 1.05 | Exceptionally satisfied
46 | 10 | 1.1
47 | 10 | 1.1
48 | 10 | 1.1
49 | 10 | 1.1
50 | 10 | 1.1

## 4_Cost Management Muliplier
% Variance | 10 | MHA Multiplier
-39% | 10 | 1.1 | 30% Contractor/70% Employer
-38% | 10 | 1.1
-37% | 10 | 1.1
-36% | 10 | 1.1
-35% | 10 | 1.1
-34% | 10 | 1.1
-33% | 10 | 1.1
-32% | 10 | 1.1
-31% | 10 | 1.1
-30% | 10 | 1.1
-29% | 10 | 1.1
-28% | 10 | 1.1
-27% | 10 | 1.1
-26% | 10 | 1.1
-25% | 10 | 1.1
-24% | 10 | 1.1
-23% | 10 | 1.1
-22% | 10 | 1.1
-20% | 9 | 1.05 | 50% Contractor/50% Employer Share
-18% | 9 | 1.05
-17% | 9 | 1.05
-16% | 9 | 1.05
-15% | 9 | 1.05
-14% | 9 | 1.05
-13% | 9 | 1.05
-12% | 9 | 1.05
-11% | 9 | 1.05
-9% | 9 | 1.05
-8% | 9 | 1.05
-7% | 9 | 1.05
-6% | 9 | 1.05
-5% | 9 | 1.05
-4% | 9 | 1.05
-3% | 8 | 1
-2% | 8 | 1
-1% | 8 | 1
0% | 8 | 1
1% | 8 | 1
2% | 8 | 1
3% | 8 | 1
4% | 5 | 0.9
5% | 5 | 0.9
6% | 5 | 0.9
7% | 5 | 0.9
8% | 5 | 0.9
9% | 5 | 0.9
10% | 5 | 0.8
11% | 2 | 0.6 | Contractor 100%/Employer 0% Share
12% | 2 | 0.6
13% | 2 | 0.6
14% | 2 | 0.6
15% | 2 | 0.6
16% | 2 | 0.6
17% | 2 | 0.6
18% | 2 | 0.6
19% | 2 | 0.6
20% | 2 | 0.6
21% | 0 | 0.5
22% | 0 | 0.5
23% | 0 | 0.5
24% | 0 | 0.5
25% | 0 | 0.5
26% | 0 | 0.5
27% | 0 | 0.5
28% | 0 | 0.5
29% | 0 | 0.5
30% | 0 | 0.5

## 10_ECI Savings Multiplier
% Saving ECI | MHA Score | MHA Multiplier
0% | 5 | 0.8
1% | 5 | 0.8
2% | 8 | 1
3% | 8 | 1
4% | 8 | 1
5% | 8 | 1
6% | 8 | 1
7% | 8 | 1
8% | 8 | 1
9% | 8 | 1
10% | 8 | 1
11% | 9 | 1.05
12% | 9 | 1.05
13% | 9 | 1.05
14% | 9 | 1.05
15% | 9 | 1.05
16% | 9 | 1.05
17% | 9 | 1.05
18% | 9 | 1.05
19% | 9 | 1.05
20% | 9 | 1.05
21% | 9 | 1.05
22% | 9 | 1.05
23% | 9 | 1.05
24% | 9 | 1.05
25% | 9 | 1.05
26% | 10 | 1.1
27% | 10 | 1.1
28% | 10 | 1.1
29% | 10 | 1.1
30% | 10 | 1.1
31% | 10 | 1.1
32% | 10 | 1.1
33% | 10 | 1.1
34% | 10 | 1.1
35% | 10 | 1.1
36% | 10 | 1.1
37% | 10 | 1.1
38% | 10 | 1.1
39% | 10 | 1.1
40% | 10 | 1.1
41% | 10 | 1.1
42% | 10 | 1.1
43% | 10 | 1.1
44% | 10 | 1.1
45% | 10 | 1.1
46% | 10 | 1.1
47% | 10 | 1.1
48% | 10 | 1.1
49% | 10 | 1.1
50% | 10 | 1.1